## Productivity
[7 empty] | Previous week Productivity | YTD Productivity new tab |  | Week | Days |  |  |  |  | LastRow | 316
[10 empty] | 1 weeks | 5
Count of Type Of Work | TOTAL | 294 | 586 | 254 | 392 | 190 | 262 | 225 | 1065575 | 213115 | 1202.0202
Office | Name | Rough QA | QA (Crew) | QA | TUT | Warranty | Rough | Trim | SQFT Production | SQFT per day | weight | SQFT to standard | Target | Emp 1st WO on this report | last WO on ytd report
Auburndale RNC | Camilo Ibar Services (sub Labor) | [5 empty] | 13 |  | 28183 | 5636.6 | 1000 | 5000 | 563.7% | 10/25/2019
Kissimmee RNC | Cesar, Dady | [5 empty] | 6 |  | 17126 | 3425.2 | 1000 | 5000 | 342.5% | 10/16/2019
St Cloud RNC | Jjany - (Sub Labor) Group - Jimmy |  | 4 |  |  |  | 7 |  | 15835 | 3167 | 1000 | 5000 | 316.7% | 10/28/2019
Kissimmee RNC | Annulysse, Jean | [5 empty] | 5 |  | 14801 | 2960.2 | 1000 | 5000 | 296% | 10/21/2019
Kissimmee RNC | DM Installation services LLC (Sub Labor) |  | 1 |  |  |  | 1 | 6 | 17282 | 3456.4 | 1500 | 7500 | 230.4% | 10/28/2019
Sanford RNC | Silverstein | [5 empty] | 5 |  | 10892 | 2178.4 | 1000 | 5000 | 217.8% | 10/17/2019
N Jacksonville RNC | Mcclough - Mcclough | [6 empty] | 7 | 15699 | 3139.8 | 1500 | 7500 | 209.3% | 10/31/2019
Tampa RNC | Ramirez,Marco |  | 5 |  |  |  | 3 | 1 | 10374 | 2074.8 | 1000 | 5000 | 207.5% | 10/28/2019
Ft Myers RNC | Lucas Cirilo, Manuel |  | 1 |  | 5 |  | 5 |  | 9807 | 1961.4 | 1000 | 5000 | 196.1% | 10/22/2019
Sanford RNC | Steven's Maintenance (Sub Labor) |  | 1 |  |  |  | 4 |  | 9406 | 1881.2 | 1000 | 5000 | 188.1% | 10/29/2019
Multi-Family | 4954 Maintenance (Sub Labor) | [6 empty] | 7 | 14105 | 2821 | 1500 | 7500 | 188.1% | 10/25/2019
Kissimmee RNC | Cruz, Kevin |  | 1 |  |  |  |  | 5 | 13810 | 2762 | 1500 | 7500 | 184.1% | 10/28/2019
Tampa RNC | Delgado, Jose |  | 7 |  |  |  | 1 | 4 | 13561 | 2712.2 | 1500 | 7500 | 180.8% | 10/25/2019
Winter Garden RNC | Tulien, Fanes |  | 1 |  |  |  | 3 |  | 8636 | 1727.2 | 1000 | 5000 | 172.7% | 10/28/2019
Kissimmee RNC | Diaz, Jorge | [5 empty] | 3 |  | 8552 | 1710.4 | 1000 | 5000 | 171% | 10/18/2019
Kissimmee RNC | AP John Nino Rivas | [5 empty] | 1 | 2 | 10577 | 2115.4 | 1250 | 6250 | 169.2% | 10/25/2019
Groveland RNC | Huggins, Gerardo | [6 empty] | 5 | 12585 | 2517 | 1500 | 7500 | 167.8% | 10/29/2019
N Jacksonville RNC | Boucher, Mathew Eugene |  | 1 |  |  |  | 4 |  | 8195 | 1639 | 1000 | 5000 | 163.9% | 10/23/2019
Melbourne RNC | Soto, Nelson | [6 empty] | 5 | 11922 | 2384.4 | 1500 | 7500 | 159% | 10/30/2019
Winter Garden RNC | Cemeco, Luis | [5 empty] | 3 |  | 7907 | 1581.4 | 1000 | 5000 | 158.1% | 10/07/2019
St Cloud RNC | Passwaters, Talen |  | 1 |  |  |  | 1 | 3 | 11543 | 2308.6 | 1500 | 7500 | 153.9% | 10/21/2019
Daytona RNC | Copeland |  | 3 |  |  |  | 1 | 5 | 11460 | 2292 | 1500 | 7500 | 152.8% | 11/01/2019
Sanford RNC | BATC Sanford |  | 1 |  |  |  | 2 | 3 | 9500 | 1900 | 1250 | 6250 | 152% | 10/24/2019
Brooksville RNC | James Cogley LLC (Sub Labor Brooksville) | [5 empty] | 3 |  | 7279 | 1455.8 | 1000 | 5000 | 145.6% | 10/25/2019
S Jacksonville RNC | Larios Construction - Kayo (Sub Labor) |  | 3 |  |  |  | 3 |  | 7277 | 1455.4 | 1000 | 5000 | 145.5% | 10/31/2019
Auburndale RNC | Torres,Jesus | [6 empty] | 5 | 10885 | 2177 | 1500 | 7500 | 145.1% | 10/30/2019
Port St Lucie RNC | Whyte | [5 empty] | 3 |  | 7220 | 1444 | 1000 | 5000 | 144.4% | 10/31/2019
Kissimmee RNC | Guzman, Jonathan | [5 empty] | 2 |  | 7174 | 1434.8 | 1000 | 5000 | 143.5% | 10/22/2019
Kissimmee RNC | Francisco Campos |  | 1 |  |  |  |  | 5 | 10535 | 2107 | 1500 | 7500 | 140.5% | 10/25/2019
Tampa RNC | McClosky, Tom | [5 empty] | 3 |  | 7022 | 1404.4 | 1000 | 5000 | 140.4% | 10/28/2019
S Jacksonville RNC | Steven Kennedy |  | 9 |  |  |  |  | 7 | 10429 | 2085.8 | 1500 | 7500 | 139.1% | 10/30/2019
Ocala RNC | Roberto Munoz | [5 empty] | 3 |  | 6748 | 1349.6 | 1000 | 5000 | 135% | 10/22/2019
Auburndale RNC | Diaz, Yidiel | [6 empty] | 5 | 9867 | 1973.4 | 1500 | 7500 | 131.6% | 10/29/2019
St Cloud RNC | Mollinedo, Darian |  | 3 |  |  |  | 3 | 1 | 6553 | 1310.6 | 1000 | 5000 | 131.1% | 10/29/2019
Ocala RNC | Steven Maculewics | [5 empty] | 3 |  | 6550 | 1310 | 1000 | 5000 | 131% | 10/24/2019
St Cloud RNC | Carranza Pierre | [5 empty] | 3 |  | 6389 | 1277.8 | 1000 | 5000 | 127.8% | 10/24/2019
S Jacksonville RNC | Alex Reyes |  | 1 |  |  |  | 3 |  | 6360 | 1272 | 1000 | 5000 | 127.2% | 10/28/2019
Tampa RNC | Williams, Charlie JR (Dad) | [5 empty] | 2 |  | 6036 | 1207.2 | 1000 | 5000 | 120.7% | 10/24/2019
Kissimmee RNC | Vega, Antonio |  | 3 |  |  |  | 2 |  | 6011 | 1202.2 | 1000 | 5000 | 120.2% | 10/21/2019
Auburndale RNC | Francisco Torres | [5 empty] | 3 |  | 5955 | 1191 | 1000 | 5000 | 119.1% | 10/22/2019
Brooksville RNC | Wienke, Adam | [5 empty] | 3 |  | 5926 | 1185.2 | 1000 | 5000 | 118.5% | 10/28/2019
Auburndale RNC | Pedraza Gonzalez, Rafael | [6 empty] | 4 | 8834 | 1766.8 | 1500 | 7500 | 117.8% | 10/25/2019
Winter Garden RNC | Espanga, Derosema | [5 empty] | 2 |  | 5880 | 1176 | 1000 | 5000 | 117.6% | 10/28/2019
Kissimmee RNC | Torres,Luis | [5 empty] | 2 |  | 5731 | 1146.2 | 1000 | 5000 | 114.6% | 10/22/2019
Venice RNC | Given,James Jr | [6 empty] | 4 | 8521 | 1704.2 | 1500 | 7500 | 113.6% | 10/30/2019
Groveland RNC | Perez, Edmundo |  | 1 |  |  |  | 3 |  | 5665 | 1133 | 1000 | 5000 | 113.3% | 10/30/2019
St Cloud RNC | Rojas, Axel |  | 3 |  |  |  | 2 | 2 | 7060 | 1412 | 1250 | 6250 | 113% | 10/29/2019
St Cloud RNC | Sandoval Luis | [5 empty] | 3 |  | 5645 | 1129 | 1000 | 5000 | 112.9% | 10/29/2019
S Jacksonville RNC | Jason Brady | [6 empty] | 5 | 8369 | 1673.8 | 1500 | 7500 | 111.6% | 10/28/2019
Auburndale RNC | Mercado, Alexander | [6 empty] | 4 | 8179 | 1635.8 | 1500 | 7500 | 109.1% | 10/25/2019
Groveland RNC | Del Valle, Emanuel | [5 empty] | 2 |  | 5441 | 1088.2 | 1000 | 5000 | 108.8% | 10/28/2019
Tampa RNC | Ramos, Jose | [5 empty] | 2 |  | 5420 | 1084 | 1000 | 5000 | 108.4% | 10/25/2019
St Cloud RNC | South Orlando Training Crew |  | 3 |  |  |  | 3 |  | 5359 | 1071.8 | 1000 | 5000 | 107.2% | 10/18/2019
Port St Lucie RNC | Wymer |  | 1 |  |  |  | 3 |  | 5330 | 1066 | 1000 | 5000 | 106.6% | 10/31/2019
St Cloud RNC | Rojas, David | [5 empty] | 3 |  | 5321 | 1064.2 | 1000 | 5000 | 106.4% | 10/29/2019
Ocala RNC | Chris Barrett | [6 empty] | 4 | 7916 | 1583.2 | 1500 | 7500 | 105.5% | 10/25/2019
Brooksville RNC | McElvain, Patrick |  | 6 |  |  |  | 3 |  | 5217 | 1043.4 | 1000 | 5000 | 104.3% | 10/28/2019
Auburndale RNC | Vega, Ramon | [6 empty] | 4 | 7808 | 1561.6 | 1500 | 7500 | 104.1% | 10/28/2019
Kissimmee RNC | Delaney Dennis |  | 2 |  |  |  | 2 |  | 5183 | 1036.6 | 1000 | 5000 | 103.7% | 10/21/2019
Sanford RNC | Crespo | [5 empty] | 3 |  | 5138 | 1027.6 | 1000 | 5000 | 102.8% | 10/30/2019
Auburndale RNC | Mario Bargaineer | [5 empty] | 3 |  | 5130 | 1026 | 1000 | 5000 | 102.6% | 10/25/2019
St Cloud RNC | Leca Jonathan | [6 empty] | 4 | 7637 | 1527.4 | 1500 | 7500 | 101.8% | 10/28/2019
Tampa RNC | Alfonso, Jose |  | 1 |  |  |  |  | 4 | 7484 | 1496.8 | 1500 | 7500 | 99.79% | 10/28/2019
Tampa RNC | Gomez, Eulalio |  | 1 |  |  |  | 2 |  | 4987 | 997.4 | 1000 | 5000 | 99.74% | 10/30/2019
Sanford RNC | North Orlando Training Crew | [5 empty] | 2 | 1 | 6182 | 1236.4 | 1250 | 6250 | 98.91% | 10/28/2019
Winter Garden RNC | Aponte, Felipe |  | 4 |  |  |  |  | 3 | 7401 | 1480.2 | 1500 | 7500 | 98.68% | 10/25/2019
St Cloud RNC | Vasquez Jose |  | 1 |  |  |  |  | 3 | 7309 | 1461.8 | 1500 | 7500 | 97.45% | 10/28/2019
Daytona RNC | Pierce_P |  | 1 |  |  |  | 2 |  | 4840 | 968 | 1000 | 5000 | 96.8% | 10/24/2019
Daytona RNC | Carcano | [6 empty] | 4 | 7247 | 1449.4 | 1500 | 7500 | 96.63% | 11/01/2019
Brooksville RNC | Moats, Clint | [5 empty] | 2 |  | 4768 | 953.6 | 1000 | 5000 | 95.36% | 10/28/2019
Sanford RNC | Meahl Gregory |  | 1 |  |  |  |  | 4 | 7140 | 1428 | 1500 | 7500 | 95.2% | 10/22/2019
Brooksville RNC | West, Matthew |  | 2 |  |  |  | 2 |  | 4756 | 951.2 | 1000 | 5000 | 95.12% | 10/28/2019
S Jacksonville RNC | Daniel Wilkinson |  | 2 | 2 |  |  | 3 |  | 4746 | 949.2 | 1000 | 5000 | 94.92% | 10/25/2019
Port St Lucie RNC | Sherba | [6 empty] | 3 | 7110 | 1422 | 1500 | 7500 | 94.8% | 10/25/2019
Brooksville RNC | Ruiz, Yamel | [6 empty] | 3 | 7072 | 1414.4 | 1500 | 7500 | 94.29% | 10/29/2019
Melbourne RNC | Oneal, Tracy |  | 1 |  |  |  | 2 |  | 4629 | 925.8 | 1000 | 5000 | 92.58% | 10/30/2019
Melbourne RNC | Gonzalez, Girardo | [5 empty] | 2 |  | 4606 | 921.2 | 1000 | 5000 | 92.12% | 10/30/2019
St Cloud RNC | Castaldi Joseph | [6 empty] | 4 | 6844 | 1368.8 | 1500 | 7500 | 91.25% | 10/28/2019
Sanford RNC | Rueben Arreola | [5 empty] | 1 | 1 | 5676 | 1135.2 | 1250 | 6250 | 90.82% | 10/24/2019
Auburndale RNC | Griffin, Nathan | [5 empty] | 2 |  | 4535 | 907 | 1000 | 5000 | 90.7% | 10/30/2019
Multi-Family | AP Morales W | [5 empty] | 1 | 2 | 5647 | 1129.4 | 1250 | 6250 | 90.35% | 10/23/2019
Tampa RNC | Berice, Derius | [6 empty] | 3 | 6708 | 1341.6 | 1500 | 7500 | 89.44% | 10/29/2019
Auburndale RNC | Acevedo, Jorge | [5 empty] | 2 |  | 4463 | 892.6 | 1000 | 5000 | 89.26% | 10/23/2019
Melbourne RNC | Webster, Garrett | 1 | 2 |  |  |  | 2 |  | 4432 | 886.4 | 1000 | 5000 | 88.64% | 10/30/2019
Port St Lucie RNC | Johnston | [6 empty] | 3 | 6607 | 1321.4 | 1500 | 7500 | 88.09% | 10/31/2019
Daytona RNC | Kilpatrick |  | 3 |  |  |  | 2 | 1 | 5351 | 1070.2 | 1250 | 6250 | 85.62% | 10/31/2019
N Jacksonville RNC | Evan Wagner LLC | [5 empty] | 2 |  | 4258 | 851.6 | 1000 | 5000 | 85.16% | 10/28/2019
St Cloud RNC | Chicoye Sadrak | [6 empty] | 3 | 6375 | 1275 | 1500 | 7500 | 85% | 10/25/2019
S Jacksonville RNC | Kirk Thomer | [5 empty] | 2 |  | 4209 | 841.8 | 1000 | 5000 | 84.18% | 10/28/2019
S Jacksonville RNC | Larios Construction - (Sub Labor) 2nd Crew | [5 empty] | 2 |  | 4136 | 827.2 | 1000 | 5000 | 82.72% | 10/31/2019
Groveland RNC | Cuba, Nerio |  | 4 |  |  |  |  | 3 | 6199 | 1239.8 | 1500 | 7500 | 82.65% | 10/29/2019
Venice RNC | Perez, Pablo JR | [5 empty] | 2 |  | 4103 | 820.6 | 1000 | 5000 | 82.06% | 10/21/2019
Ft Myers RNC | Safford, Joe |  |  | 1 | 3 |  | 2 |  | 4084 | 816.8 | 1000 | 5000 | 81.68% | 10/15/2019
Brooksville RNC | Tirado, Omar | [5 empty] | 2 |  | 4079 | 815.8 | 1000 | 5000 | 81.58% | 10/28/2019
Venice RNC | Kendrick, Jereme |  |  |  | 1 |  | 2 |  | 4079 | 815.8 | 1000 | 5000 | 81.58% | 10/29/2019
Venice RNC | Sprague, Alec |  | 5 |  | 4 |  |  | 3 | 6103 | 1220.6 | 1500 | 7500 | 81.37% | 10/30/2019
Daytona RNC | Stevenson | [6 empty] | 3 | 6077 | 1215.4 | 1500 | 7500 | 81.03% | 10/29/2019
Port St Lucie RNC | Buell | [5 empty] | 2 |  | 4028 | 805.6 | 1000 | 5000 | 80.56% | 10/28/2019
Tampa RNC | Gonzalez, Francisco | [5 empty] | 2 |  | 3973 | 794.6 | 1000 | 5000 | 79.46% | 10/31/2019
Kissimmee RNC | Ayala Guzman |  | 3 |  |  |  | 1 |  | 3826 | 765.2 | 1000 | 5000 | 76.52% | 10/15/2019
Auburndale RNC | Camilo Ibar (Miguel) | [5 empty] | 1 |  | 3773 | 754.6 | 1000 | 5000 | 75.46% | 10/25/2019
Auburndale RNC | Adkins,Charles | [6 empty] | 3 | 5659 | 1131.8 | 1500 | 7500 | 75.45% | 10/28/2019
Winter Garden RNC | Ponce, Jose |  | 1 |  |  |  |  | 2 | 5581 | 1116.2 | 1500 | 7500 | 74.41% | 10/25/2019
Venice RNC | Cadet, Paul |  |  |  | 2 |  | 2 |  | 3717 | 743.4 | 1000 | 5000 | 74.34% | 10/24/2019
Port St Lucie RNC | Yepez | [6 empty] | 3 | 5537 | 1107.4 | 1500 | 7500 | 73.83% | 10/29/2019
Auburndale RNC | Mojica,Eddie | [5 empty] | 2 |  | 3673 | 734.6 | 1000 | 5000 | 73.46% | 10/25/2019
N Jacksonville RNC | Sergio Martinez |  | 1 |  |  |  | 2 |  | 3664 | 732.8 | 1000 | 5000 | 73.28% | 10/22/2019
Sanford RNC | Austin, James |  |  |  | 1 |  | 2 |  | 3656 | 731.2 | 1000 | 5000 | 73.12% | 10/24/2019
Groveland RNC | Reynoso, Ramon |  | 3 |  |  |  | 2 |  | 3647 | 729.4 | 1000 | 5000 | 72.94% | 10/31/2019
N Jacksonville RNC | Travis Brown |  | 2 |  |  |  | 2 |  | 3640 | 728 | 1000 | 5000 | 72.8% | 10/22/2019
Venice RNC | Cabrera, Ramon |  |  |  | 2 |  | 2 |  | 3538 | 707.6 | 1000 | 5000 | 70.76% | 10/28/2019
Daytona RNC | Connolly | [5 empty] | 2 |  | 3526 | 705.2 | 1000 | 5000 | 70.52% | 10/30/2019
Winter Garden RNC | Algarin, Joel | [6 empty] | 2 | 5287 | 1057.4 | 1500 | 7500 | 70.49% | 10/25/2019
Sanford RNC | Kelly (Sub Labor) | [6 empty] | 2 | 5224 | 1044.8 | 1500 | 7500 | 69.65% | 10/28/2019
Daytona RNC | Whited | [5 empty] | 2 |  | 3477 | 695.4 | 1000 | 5000 | 69.54% | 10/24/2019
Auburndale RNC | Wolf, David | [5 empty] | 2 |  | 3465 | 693 | 1000 | 5000 | 69.3% | 10/24/2019
Ocala RNC | Switzer, Justin |  | 1 |  |  |  | 1 | 1 | 4329 | 865.8 | 1250 | 6250 | 69.26% | 10/24/2019
Groveland RNC | Morocho, Danny |  | 5 |  |  |  |  | 2 | 5192 | 1038.4 | 1500 | 7500 | 69.23% | 10/29/2019
Winter Garden RNC | Valverde, Armando |  | 1 |  |  |  |  | 2 | 5190 | 1038 | 1500 | 7500 | 69.2% | 10/25/2019
Tampa RNC | Smith, Jesse |  | 1 |  |  |  |  | 2 | 5128 | 1025.6 | 1500 | 7500 | 68.37% | 10/29/2019
Tampa RNC | Espinosa, Roy | [5 empty] | 2 |  | 3391 | 678.2 | 1000 | 5000 | 67.82% | 10/24/2019
Tampa RNC | Rojas, Yarian | [5 empty] | 2 |  | 3385 | 677 | 1000 | 5000 | 67.7% | 10/28/2019
S Jacksonville RNC | Marshall Depreist (AP) |  | 1 |  |  |  | 2 |  | 3352 | 670.4 | 1000 | 5000 | 67.04% | 10/25/2019
St Cloud RNC | Rivera Robert |  | 1 |  |  |  | 2 |  | 3301 | 660.2 | 1000 | 5000 | 66.02% | 10/29/2019
Sanford RNC | Anes, Roberto |  | 1 |  |  |  | 1 |  | 3263 | 652.6 | 1000 | 5000 | 65.26% | 10/24/2019
N Jacksonville RNC | Aleksander Moroz | [5 empty] | 1 |  | 3231 | 646.2 | 1000 | 5000 | 64.62% | 10/24/2019
Ft Myers RNC | Breese, Jonathan |  | 1 |  |  |  |  | 3 | 4827 | 965.4 | 1500 | 7500 | 64.36% | 10/24/2019
St Cloud RNC | Rivera Nelson | [6 empty] | 2 | 4811 | 962.2 | 1500 | 7500 | 64.15% | 10/25/2019
Ft Myers RNC | Fabergas, Rolando |  | 1 |  |  |  |  | 2 | 4736 | 947.2 | 1500 | 7500 | 63.15% | 10/28/2019
Venice RNC | Hanson, Travis | [6 empty] | 2 | 4674 | 934.8 | 1500 | 7500 | 62.32% | 10/28/2019
Ocala RNC | Devin Dickinson |  |  |  | 1 |  | 2 |  | 3088 | 617.6 | 1000 | 5000 | 61.76% | 10/24/2019
Ft Myers RNC | Suri, Javier | [5 empty] | 2 |  | 3038 | 607.6 | 1000 | 5000 | 60.76% | 10/25/2019
Brooksville RNC | Nevares, Jesus | [6 empty] | 2 | 4548 | 909.6 | 1500 | 7500 | 60.64% | 10/31/2019
Sanford RNC | Mitchell |  | 2 |  |  |  |  | 2 | 4394 | 878.8 | 1500 | 7500 | 58.59% | 10/22/2019
Auburndale RNC | Hartley, Thomas | [5 empty] | 1 |  | 2902 | 580.4 | 1000 | 5000 | 58.04% | 10/28/2019
Winter Garden RNC | De Jesus, Pedro |  | 4 |  |  |  | 1 |  | 2866 | 573.2 | 1000 | 5000 | 57.32% | 10/28/2019
Port St Lucie RNC | Peterson, Rodrick |  | 1 |  |  |  | 1 | 1 | 3511 | 702.2 | 1250 | 6250 | 56.18% | 10/30/2019
Tampa RNC | Laura, Patrick | [6 empty] | 2 | 4199 | 839.8 | 1500 | 7500 | 55.99% | 10/29/2019
Sanford RNC | Nelms Dynasty (sub Labor) |  | 2 |  |  |  | 1 |  | 2769 | 553.8 | 1000 | 5000 | 55.38% | 10/25/2019
Tampa RNC | Annicaro, Thomas |  | 2 |  |  |  | 1 |  | 2756 | 551.2 | 1000 | 5000 | 55.12% | 10/24/2019
Daytona RNC | Consalo |  | 1 |  |  |  | 1 | 1 | 3343 | 668.6 | 1250 | 6250 | 53.49% | 10/25/2019
Kissimmee RNC | Z Torres, David (QA) |  | 4 | 19 |  |  |  | 1 | 3981 | 796.2 | 1500 | 7500 | 53.08% | 10/14/2019
Groveland RNC | Christie, Norman |  | 1 |  |  |  | 1 |  | 2601 | 520.2 | 1000 | 5000 | 52.02% | 10/25/2019
Auburndale RNC | Eodice, Cody |  | 1 |  |  |  | 1 |  | 2599 | 519.8 | 1000 | 5000 | 51.98% | 10/30/2019
Auburndale RNC | Pace, Melvin | [6 empty] | 2 | 3844 | 768.8 | 1500 | 7500 | 51.25% | 10/25/2019
Kissimmee RNC | AP Javier Lopez | [6 empty] | 1 | 3826 | 765.2 | 1500 | 7500 | 51.01% | 10/29/2019
Kissimmee RNC | Maldonado | [6 empty] | 1 | 3802 | 760.4 | 1500 | 7500 | 50.69% | 10/25/2019
Sanford RNC | AP Suheidy Vega Torres | [6 empty] | 1 | 3791 | 758.2 | 1500 | 7500 | 50.55% | 10/28/2019
Winter Garden RNC | Del Valle, David |  | 3 |  |  |  | 1 |  | 2500 | 500 | 1000 | 5000 | 50% | 10/28/2019
Winter Garden RNC | Olivero, Moises Concepcion |  | 1 |  |  |  | 1 |  | 2500 | 500 | 1000 | 5000 | 50% | 10/23/2019
Venice RNC | Santana, Yunior |  | 1 |  |  |  | 1 |  | 2432 | 486.4 | 1000 | 5000 | 48.64% | 10/25/2019
Ft Myers RNC | Allen, Sean | [6 empty] | 2 | 3644 | 728.8 | 1500 | 7500 | 48.59% | 10/30/2019
Sanford RNC | Tanner |  | 2 | 2 |  |  |  | 2 | 3596 | 719.2 | 1500 | 7500 | 47.95% | 10/28/2019
Sanford RNC | Fleming |  | 1 |  | 2 |  | 1 |  | 2395 | 479 | 1000 | 5000 | 47.9% | 10/29/2019
S Jacksonville RNC | Darren Ferrell |  | 3 |  |  |  | 1 |  | 2298 | 459.6 | 1000 | 5000 | 45.96% | 10/31/2019
Winter Garden RNC | Santiago, Edwin | [5 empty] | 1 |  | 2278 | 455.6 | 1000 | 5000 | 45.56% | 10/25/2019
Kissimmee RNC | Elias |  | 1 |  |  |  | 1 |  | 2267 | 453.4 | 1000 | 5000 | 45.34% | 10/28/2019
Brooksville RNC | Gerholdt,Brendan |  | 3 |  |  |  | 1 |  | 2247 | 449.4 | 1000 | 5000 | 44.94% | 10/25/2019
Melbourne RNC | Reis, Kurt | [5 empty] | 1 |  | 2234 | 446.8 | 1000 | 5000 | 44.68% | 10/30/2019
Kissimmee RNC | (AP) Jose Blanco | [6 empty] | 1 | 3348 | 669.6 | 1500 | 7500 | 44.64% | 10/29/2019
S Jacksonville RNC | Byers, Jerad |  | 1 |  |  |  | 1 |  | 2216 | 443.2 | 1000 | 5000 | 44.32% | 11/01/2019
Kissimmee RNC | (AP) Arroyo Burgos, Jose |  | 1 |  |  |  |  | 1 | 3275 | 655 | 1500 | 7500 | 43.67% | 10/24/2019
Brooksville RNC | Marquez, Alexis | [6 empty] | 2 | 3130 | 626 | 1500 | 7500 | 41.73% | 10/29/2019
Multi-Family | Fort Solutions LLC (Sub Labor) | [5 empty] | 1 |  | 2082 | 416.4 | 1000 | 5000 | 41.64% | 10/30/2019
Groveland RNC | Quinones, Ray Jr | [5 empty] | 1 |  | 2061 | 412.2 | 1000 | 5000 | 41.22% | 10/31/2019
Venice RNC | Ponce, Adonis |  | 1 |  | 1 |  | 1 |  | 2061 | 412.2 | 1000 | 5000 | 41.22% | 10/29/2019
Tampa RNC | Boyd, Dave | [5 empty] | 1 |  | 2034 | 406.8 | 1000 | 5000 | 40.68% | 10/28/2019
S Jacksonville RNC | Nathan Hardy | [5 empty] | 1 |  | 1994 | 398.8 | 1000 | 5000 | 39.88% | 10/24/2019
Port St Lucie RNC | Mitchell Munroe |  | 1 |  |  |  | 1 |  | 1992 | 398.4 | 1000 | 5000 | 39.84% | 10/29/2019
Daytona RNC | Seraphin Antoine | [5 empty] | 1 |  | 1983 | 396.6 | 1000 | 5000 | 39.66% | 10/28/2019
Sanford RNC | Timothy Raymond | [6 empty] | 2 | 2956 | 591.2 | 1500 | 7500 | 39.41% | 10/23/2019
Winter Garden RNC | Pirela, Carlos |  | 1 |  |  |  |  | 1 | 2769 | 553.8 | 1500 | 7500 | 36.92% | 10/29/2019
Groveland RNC | Delgado, Jesus | [5 empty] | 1 |  | 1828 | 365.6 | 1000 | 5000 | 36.56% | 10/23/2019
Ocala RNC | ZZ John Seegers Rough QA | 11 |  | 1 | 7 |  | 1 |  | 1828 | 365.6 | 1000 | 5000 | 36.56% | 10/29/2019
St Cloud RNC | Jackson Trelon | [5 empty] | 1 |  | 1828 | 365.6 | 1000 | 5000 | 36.56% | 10/28/2019
Brooksville RNC | Keys, Michael | [5 empty] | 1 |  | 1816 | 363.2 | 1000 | 5000 | 36.32% | 10/28/2019
Auburndale RNC | Camilo Ibar (Alberto) | [5 empty] | 1 |  | 1811 | 362.2 | 1000 | 5000 | 36.22% | 10/25/2019
Sanford RNC | Edwards | [6 empty] | 1 | 2704 | 540.8 | 1500 | 7500 | 36.05% | 10/31/2019
Kissimmee RNC | Francisco Reccy De Leon | [5 empty] | 1 |  | 1753 | 350.6 | 1000 | 5000 | 35.06% | 10/26/2019
Sanford RNC | Duxbury |  | 2 |  |  |  | 1 |  | 1729 | 345.8 | 1000 | 5000 | 34.58% | 10/22/2019
Kissimmee RNC | Martinez, Marycarmen |  | 2 |  |  |  |  | 1 | 2578 | 515.6 | 1500 | 7500 | 34.37% | 10/25/2019
Tampa RNC | Z Perez, Yanier (QA) |  |  | 5 |  | 4 | 1 |  | 1693 | 338.6 | 1000 | 5000 | 33.86% | 10/28/2019
N Jacksonville RNC | Alexander Pecherin | [6 empty] | 1 | 2511 | 502.2 | 1500 | 7500 | 33.48% | 10/25/2019
Brooksville RNC | Mcvey, Kyle | [5 empty] | 1 |  | 1672 | 334.4 | 1000 | 5000 | 33.44% | 10/24/2019
Tampa RNC | Pipe, Anthony |  | 10 | 5 |  |  |  | 1 | 2503 | 500.6 | 1500 | 7500 | 33.37% | 11/01/2019
Sanford RNC | Bassett | 1 | [5 empty] | 1 | 2471 | 494.2 | 1500 | 7500 | 32.95% | 09/12/2019
Auburndale RNC | Camilo Ibar (Misael) | [5 empty] | 1 |  | 1644 | 328.8 | 1000 | 5000 | 32.88% | 10/28/2019
St Cloud RNC | Jason locorini | [6 empty] | 1 | 2362 | 472.4 | 1500 | 7500 | 31.49% | 10/23/2019
Venice RNC | Florida's Choice (Sub Labor) | [5 empty] | 1 |  | 1504 | 300.8 | 1000 | 5000 | 30.08% | 10/30/2019
Brooksville RNC | Diaz,Delia |  | 1 |  |  |  |  | 1 | 2247 | 449.4 | 1500 | 7500 | 29.96% | 10/28/2019
Sanford RNC | AP Elswoth Busano | [6 empty] | 1 | 2204 | 440.8 | 1500 | 7500 | 29.39% | 10/28/2019
Daytona RNC | Rivera, Felix | [5 empty] | 1 |  | 1463 | 292.6 | 1000 | 5000 | 29.26% | 10/25/2019
S Jacksonville RNC | Smith | [6 empty] | 1 | 2129 | 425.8 | 1500 | 7500 | 28.39% | 10/01/2019
Kissimmee RNC | Diaz, Daniel |  | 2 |  |  |  |  | 1 | 1946 | 389.2 | 1500 | 7500 | 25.95% | 07/16/2019
Daytona RNC | AP Stramondo | [6 empty] | 1 | 1875 | 375 | 1500 | 7500 | 25% | 10/28/2019
Sanford RNC | AP William Pond | [6 empty] | 1 | 1811 | 362.2 | 1500 | 7500 | 24.15% | 10/28/2019
Auburndale RNC | Z Rivera, Corey (QA) |  | 21 | 9 |  |  |  | 1 | 1541 | 308.2 | 1500 | 7500 | 20.55% | 10/31/2019
Brooksville RNC | Concepcion, Moises |  | 1 |  |  |  |  | 1 | 1273 | 254.6 | 1500 | 7500 | 16.97% | 10/30/2019
Auburndale RNC | ZZ Ramirez, Frank Rough QA | 10 | [11 empty] | 10/30/2019
Auburndale RNC | Y Blue, Ricky (TUT) |  |  |  | 12 | [8 empty] | 11/01/2019
Auburndale RNC | ZZ Adkins, Scott Rough QA | 9 | [11 empty] | 10/30/2019
Auburndale RNC | Z Dickinson, Marvin (QA) |  |  |  |  | 18 | [7 empty] | 10/29/2019
Auburndale RNC | ZZ Strickler, Alan Rough QA | 13 | [11 empty] | 10/28/2019
Auburndale RNC | Z Christian, Paul (QA) |  | 13 | 9 |  | 1 | [7 empty] | 10/28/2019
Auburndale RNC | Z Maxson, Damien (QA) |  | 4 | 5 | [9 empty] | 10/31/2019
Auburndale RNC | Z Owen, Kevin (QA) |  | 12 | 1 |  | 3 | [7 empty] | 10/31/2019
Auburndale RNC | Y Beoto, Juan (TUT) |  | 4 |  | 24 | [8 empty] | 10/28/2019
Auburndale RNC | Y Morales, Jose (TUT) |  | 1 |  | 29 | [8 empty] | 10/29/2019
Brooksville RNC | ZZ Concepcion, Gladdys (ROUGH QA) | 10 | 3 | [10 empty] | 11/03/2019
Brooksville RNC | Z Leal, Wilmer (QA) |  | 6 | 10 |  | 4 | [7 empty] | 10/28/2019
Brooksville RNC | ZZ Hooker, Freddie ROUGH QA | 2 | 1 | [10 empty] | 10/31/2019
Brooksville RNC | Y Gonzalez, Joan (TUT) |  | 6 |  | 19 | [8 empty] | 10/30/2019
Brooksville RNC | ZZ Murch, Robert ROUGH QA | 3 | 2 | [10 empty] | 10/28/2019
Brooksville RNC | Z Vega, Mike (QA) | 1 | 6 | 2 |  | 2 | [7 empty] | 10/28/2019
Brooksville RNC | Z Jutte, Thomas (QA) |  | 16 | 3 |  | 2 | [7 empty] | 10/31/2019
Brooksville RNC | Y Fortner, Russell (TUT) |  | 15 |  | 20 | [8 empty] | 10/30/2019
Custom ORL | Adam Unger |  |  |  | 1 | [8 empty] | 10/31/2019
Daytona RNC | ZZ Dean, Phillip ROUGH QA | 9 | [11 empty] | 10/23/2019
Daytona RNC | ZZ Bowers, Zachary ROUGH QA | 15 | [11 empty] | 10/24/2019
Daytona RNC | Z Echevarria (QA) | [12 empty] | 10/29/2019
Daytona RNC | Z Waggoner, Nathaniel (QA) |  | 7 | 4 |  | 4 | [7 empty] | 10/31/2019
Daytona RNC | Y DeWitt, Brett (TUT) |  |  |  | 4 | [8 empty] | 10/30/2019
Daytona RNC | Y Whitaker, Christopher (TUT) |  | 7 |  | 17 | [8 empty] | 10/30/2019
Daytona RNC | Z Moussette, Frank (QA) |  | 4 | 11 |  | 3 | [7 empty] | 11/01/2019
Ft Myers RNC | Z Duran, Eudy (QA) |  |  | 5 |  | 1 | [7 empty] | 10/25/2019
Ft Myers RNC | Montejo, Maria |  | 2 |  | 2 | [8 empty] | 10/31/2019
Ft Myers RNC | ZZ Steyskal, Nathan Rough QA | 12 |  | 1 | [9 empty] | 10/22/2019
Ft Myers RNC | Y Wade, Antonio (TUT) |  |  | 1 | 6 | [8 empty] | 10/15/2019
Groveland RNC | ZZ Aleman, Felix Rough QA | 2 | [11 empty] | 10/29/2019
Groveland RNC | Z Nunez, Julio (QA) |  | 1 | 3 |  | 4 | [7 empty] | 10/25/2019
Groveland RNC | Y Silguero, Ricardo (TUT) |  |  |  | 18 | [8 empty] | 10/30/2019
Groveland RNC | ZZ Herrera, Alvaro Rough QA | 8 | [11 empty] | 10/30/2019
Groveland RNC | ZZ Quinones, Ray Rough QA | 3 | [11 empty] | 10/25/2019
Groveland RNC | Z Giraldo, David Andres (QA) |  | 4 | 3 |  | 3 | [7 empty] | 10/29/2019
Kissimmee RNC | Aguayo, Antonio |  | 1 | [10 empty] | 10/17/2019
Kissimmee RNC | ZZ Pereira, Decio Rough QA | 9 |  | 1 | [9 empty] | 10/17/2019
Kissimmee RNC | ZZ Camacho, Andre Rough QA | 8 | [11 empty] | 10/25/2019
Kissimmee RNC | ZZ Guzman, Lisandro Rough QA | 16 | [11 empty] | 10/28/2019
Kissimmee RNC | Z Curtis, Johnson (QA) |  |  | 4 |  | 11 | [7 empty] | 11/01/2019
Kissimmee RNC | Z Inderjit, Avinash (QA) |  |  | 3 | [9 empty] | 10/16/2019
Kissimmee RNC | Martinez, Luis |  | 2 | [10 empty] | 10/22/2019
Kissimmee RNC | Aguayo, Jose | [12 empty] | 10/24/2019
Kissimmee RNC | Y Cruz Andricain, Julio C (TUT) |  | 1 |  | 26 | [8 empty] | 10/15/2019
Kissimmee RNC | ZZ Pereira, Decio D'icarahy | 1 | [11 empty] | 10/25/2019
Melbourne RNC | ZZ Sevcik, Eric ROUGH QA |  |  |  |  | 1 | [7 empty] | 10/29/2019
Melbourne RNC | Richey, Kyle |  | 7 | [10 empty] | 10/30/2019
Melbourne RNC | Z Long, Jordan (QA) | 1 | 15 | 1 | 3 | [8 empty] | 10/30/2019
Melbourne RNC | Z Dean, Art (QA) |  | 15 | [10 empty] | 10/29/2019
Melbourne RNC | Z Baird, Chris (QA) |  | 4 | 2 | [9 empty] | 10/29/2019
Melbourne RNC | Rogers, Mike |  | 4 | [10 empty] | 10/29/2019
Melbourne RNC | ZZ Ron Krueger Rough QA |  | 2 |  | 3 | [8 empty] | 10/28/2019
Multi-Family | ZZ Dallos, Francisco Rough QA |  | 1 |  | 4 | [8 empty] | 09/09/2019
Multi-Family | Z Ramdeen (QA) |  |  | 11 |  | 6 | [7 empty] | 10/30/2019
Multi-Family | Z Casas, Mauricio (QA) |  |  |  |  | 5 | [7 empty] | 11/01/2019
Multi-Family | Randy Silguero |  | 2 | [10 empty] | 10/29/2019
Multi-Family | Kelvin Febus Centeno |  |  |  | 1 | [8 empty] | 10/30/2019
N Jacksonville RNC | Z Donald, Russ (QA) |  | 14 | 8 |  | 3 | [7 empty] | 10/28/2019
N Jacksonville RNC | Y Brent Blair (TUT) |  | 20 |  | 12 | [8 empty] | 10/25/2019
N Jacksonville RNC | ZZ Monk, Adam Rough QA | 11 |  | 1 | [9 empty] | 10/25/2019
N Jacksonville RNC | Z Corey, Blake (QA) |  | 19 | 3 |  | 1 | [7 empty] | 10/30/2019
Ocala RNC | Carl (Temp) |  |  | 2 | 3 | [8 empty] | 10/29/2019
Ocala RNC | Z Scarberry, Dana (QA) |  | 8 | 4 | 2 | [8 empty] | 10/28/2019
Port St Lucie RNC | Z Clemmons, Marshannon (QA) |  | 9 | 2 | 7 | 4 | [7 empty] | 10/31/2019
Port St Lucie RNC | ZZ Perlmutter, Mark ROUGH QA | 8 | [11 empty] | 10/28/2019
Port St Lucie RNC | Z Berkoben, Jason (QA) |  | 25 | 6 |  | 5 | [7 empty] | 10/29/2019
S Jacksonville RNC | ZZ Rose, Geno Rough QA | 14 | 1 | [10 empty] | 10/30/2019
S Jacksonville RNC | ZZ Otis, Ditannon Rough QA | 12 | 1 | [10 empty] | 11/01/2019
S Jacksonville RNC | Z Page, Terry (QA) |  | 7 | 4 |  | 12 | [7 empty] | 10/28/2019
S Jacksonville RNC | Y Baltazar, Abimael (TUT) |  | 13 |  | 23 | [8 empty] | 10/30/2019
Sanford RNC | Z Greene, Matthew (QA) |  | 2 | 6 | 5 | 5 | [7 empty] | 11/01/2019
Sanford RNC | Z Browning, Scott (QA) |  |  | 3 |  | 5 | [7 empty] | 10/29/2019
Sanford RNC | Z Morrill, Christopher (QA) |  |  | 13 | 1 | 6 | [7 empty] | 10/29/2019
Sanford RNC | Ramirez |  | 4 | [10 empty] | 10/25/2019
Sanford RNC | Z Czerniawski, Joseph (QA) |  |  | 1 |  | 9 | [7 empty] | 10/31/2019
Sanford RNC | ZZ Dunbar, Jeremy ROUGH QA | 5 | [11 empty] | 10/17/2019
Sanford RNC | Y Rohr, Michael (TUT) |  |  |  | 7 | [8 empty] | 10/29/2019
Sanford RNC | ZZ Baker, Chris ROUGH QA | 2 | 1 |  | 2 | [8 empty] | 11/01/2019
Sanford RNC | ZZ Bogue, Brandon ROUGH QA | 17 |  | 1 | 5 | [8 empty] | 10/18/2019
Sanford RNC | ZZ Continanzi, James ROUGH QA | 10 | [11 empty] | 10/14/2019
Sanford RNC | ZZ Meier, Jeremy Rough QA | 4 |  | 3 | [9 empty] | 10/28/2019
Sanford RNC | Y Jose Santiago (TUT) |  |  |  | 13 | [8 empty] | 10/31/2019
Sanford RNC | Z Curry, Darryl (QA) |  |  | 12 |  | 2 | [7 empty] | 11/01/2019
Service ORL | Rod Ohlsen | [12 empty] | 11/02/2019
Service ORL | JAX - Luis Quero | [12 empty] | 10/29/2019
Service TPA | Carrigan | [12 empty] | 10/30/2019
Service TPA | Racel, Derek | [12 empty] | 10/28/2019
Service TPA | Nestor Mathurin Toussaint | [12 empty] | 10/31/2019
St Cloud RNC | Y Jarvis, Michael (TUT) |  |  |  | 14 | [8 empty] | 10/23/2019
St Cloud RNC | Z Harris, James (QA) |  | 4 | 16 |  | 9 | [7 empty] | 10/30/2019
St Cloud RNC | Y Harf, Keith (TUT) |  |  |  | 15 | [8 empty] | 10/17/2019
St Cloud RNC | ZZ David De-Grasse Rough QA | 7 |  | 1 | [9 empty] | 11/03/2019
St Cloud RNC | Z Rivera, Wylmer (QA) |  | 1 | 3 |  | 2 | [7 empty] | 10/28/2019
St Cloud RNC | ZZ Liles, Isaac Rough QA | 1 | [11 empty] | 10/31/2019
St Cloud RNC | ZZ Leon, Humberto Rough QA | 8 | [11 empty] | 10/28/2019
St Cloud RNC | ZZ Leija, Diego Rough QA | 4 | [11 empty] | 10/29/2019
St Cloud RNC | Z Santos, Juan (QA) |  |  | 6 |  | 3 | [7 empty] | 10/31/2019
Tampa RNC | Y Cordovi, Carlos (TUT) |  | 6 |  | 10 | [8 empty] | 11/01/2019
Tampa RNC | Z McCord, Michael (QA) |  | 14 | 5 |  | 8 | [7 empty] | 11/01/2019
Tampa RNC | Rodriguez, Emilio |  |  |  | 2 | [8 empty] | 10/25/2019
Tampa RNC | Y Cruz, Jalierky (TUT) |  | 15 |  | 7 | [8 empty] | 10/28/2019
Tampa RNC | ZZ Miguel Concepcion ROUGH QA | 7 | 2 | [10 empty] | 10/29/2019
Tampa RNC | ZZ Rodriguez, Eder ROUGH QA | 17 | [11 empty] | 10/28/2019
Tampa RNC | ZZ Severe, Anthony ROUGH QA | 3 | [11 empty] | 10/28/2019
Tampa RNC | Z Baboolal, Gayah (QA) |  |  | 2 |  | 10 | [7 empty] | 10/28/2019
Tampa RNC | ZZ Boucher, James ROUGH QA |  |  | 1 | [9 empty] | 09/16/2019
Tampa RNC | ZZ Wright, Edward ROUGH QA |  | 1 | [10 empty] | 10/31/2019
Tampa RNC | Y Martin, Nick (TUT) |  | 3 |  | 7 | [8 empty] | 10/30/2019
Venice RNC | z Stilwell, Jerrold (QA) |  | 6 | 2 | 3 | [8 empty] | 10/31/2019
Venice RNC | Z Diehl, Peter (QA) |  | 2 | 2 | 5 | 4 | [7 empty] | 11/01/2019
Venice RNC | ZZ Palmucci, James ROUGH QA | 6 | [11 empty] | 10/30/2019
Venice RNC | ZZ Rodriguez, Pedro ROUGH QA | 5 | [11 empty] | 10/30/2019
Venice RNC | Z Nichols, John (Butch) (QA) |  | 10 | 1 |  | 7 | [7 empty] | 10/31/2019
Winter Garden RNC | Z Jeantilhomme, Charite (QA) |  | 11 | 7 |  | 3 | [7 empty] | 10/28/2019
Winter Garden RNC | Z - Taveras, Marino (QA) |  | 17 | 2 |  | 8 | [7 empty] | 10/31/2019
Winter Garden RNC | Rodriguez, Leonardo |  | 7 | [10 empty] | 10/30/2019
Winter Garden RNC | ZZ Alderman, Jody Rough QA | 1 | [11 empty] | 10/31/2019
Winter Garden RNC | ZZ Robles, Jared Rough QA |  |  | 1 |  | 1 | [7 empty] | 10/28/2019
Winter Garden RNC | ZZ Ellis, Berman Rough QA | 2 | 4 | 1 | [9 empty] | 10/30/2019
Winter Garden RNC | Y - Jackson, Amechi (TUT) |  |  |  | 31 | [8 empty] | 10/29/2019
Winter Garden RNC | Z Johnson, Paul (QA) | 5 |  | 11 |  | 11 | [7 empty] | 11/01/2019

## TUT Report
[6 empty] | TUG | TUG | LastRow | 83
UG
Count of Type Of Work |  |  | 3 |  |  |  | T-Pole
Office | Crew | Total | # active tuts | avg per Day | % To Target 35
Auburndale RNC
| Y Blue, Ricky (TUT) | 12
| Y Beoto, Juan (TUT) | 24
| Y Morales, Jose (TUT) | 29
0
0
Auburndale RNC Total |  | 65 | 3 | 4.3333 | 61.9%
Brooksville RNC
| Y Gonzalez, Joan (TUT) | 19
| Y Fortner, Russell (TUT) | 20
0
0
0
Brooksville RNC Total |  | 39 | 2 | 3.9 | 55.71%
Daytona RNC
| Y DeWitt, Brett (TUT) | 4
| Y Whitaker, Christopher (TUT) | 17
0
0
0
Daytona RNC Total |  | 21 | 2 | 2.1 | 30%
FT Myers RNC
| Y Blue, Ricky (TUT) | 0
0
0
0
0
FT Myers RNC |  | 0 | 1 | 0 | 0%
Groveland RNC
| Y Silguero, Ricardo (TUT) | 18
0
0
0
0
Groveland RNC Total |  | 18 | 1 | 3.6 | 51.43%
Kissimmee RNC
| Y Cruz Andricain, Julio C (TUT) | 26
0
0
0
0
Kissimmee RNC Total |  | 26 | 1 | 5.2 | 74.29%
Melbourne RNC
0
0
0
0
0
Melbourne RNC |  | 0 | 0
N Jacksonville RNC
| Y Brent Blair (TUT) | 12
0
0
0
0
N Jacksonville RNC Total |  | 12 | 1 | 2.4 | 34.29%
Ocala RNC
0
0
0
0
0
Ocala RNC Total |  | 0 | 0
Port St Lucie RNC
0
0
0
0
0
Port St Lucie RNC Total |  | 0 | 0
S Jacksonville RNC
| Y Baltazar, Abimael (TUT) | 23
0
0
0
0
S Jacksonville RNC Total |  | 23 | 1 | 4.6 | 65.71%
Sanford RNC
| Y Rohr, Michael (TUT) | 7
| Y Jose Santiago (TUT) | 13
0
0
0
Sanford RNC Total |  | 20 | 2 | 2 | 28.57%
St Cloud RNC
| Y Jarvis, Michael (TUT) | 14
| Y Harf, Keith (TUT) | 15
0
0
0
St Cloud RNC Total |  | 29 | 2 | 2.9 | 41.43%
Tampa RNC
| Y Cordovi, Carlos (TUT) | 10
| Y Cruz, Jalierky (TUT) | 7
| Y Martin, Nick (TUT) | 7
0
0
Tampa RNC Total |  | 24 | 3 | 1.6 | 22.86%
Venice RNC
0
0
0
0
0
Venice RNC Total |  | 0 | 0
Winter Garden RNC
| Y - Jackson, Amechi (TUT) | 31
0
0
0
0
Winter Garden RNC Total |  | 31 | 1 | 6.2 | 88.57%
Multi-Family
| Y Cruz Andricain, Julio C (TUT) | 16
0
0
0
0
Multi-Family |  | 16 | 1 | 3.2 | 45.71%
Grand Total |  | 324 | 21 | 3.0857 | 44.08%

## QA Report
[7 empty] | TUG | TUG | Phases | Target | 20 | LastRow | 148
[8 empty] | UG | Warranty
Count of Type Of Work |  |  |  |  | 5 | days in a week |  | T-Pole | QA
Office | QACrew | SQ-FT | Total | # active tuts | avg per Day | % To Target 20
Auburndale RNC
| Z Rivera, Corey (QA) | 19389 | 9
| Z Dickinson, Marvin (QA) | 39460 | 18
| Z Christian, Paul (QA) | 20186 | 10
| Z Maxson, Damien (QA) | 9159 | 5
| Z Owen, Kevin (QA) | 7816 | 4
0
0
0
0
0
Auburndale RNC Total | Total | 96010 | 46 | 5 | 1.84 | 46%
Brooksville RNC
| Z Leal, Wilmer (QA) | 30292 | 14
| Z Vega, Mike (QA) | 14139 | 4
| Z Jutte, Thomas (QA) | 11608 | 5
0
0
0
0
0
0
Brooksville RNC Total | Total | 56039 | 23 | 3 | 1.5333 | 38.33%
Daytona RNC
| Z Waggoner, Nathaniel (QA) | 18725 | 8
| Z Moussette, Frank (QA) | 25811 | 14
0
0
0
0
Daytona RNC Total | Total | 44536 | 22 | 2 | 2.2 | 55%
Ft Myers RNC
| Z Duran, Eudy (QA) | 12066 | 6
0
0
0
0
0
0
0
Ft Myers RNC | Total | 12066 | 6 | 1 | 1.2 | 30%
Groveland RNC
| Z Nunez, Julio (QA) | 13629 | 7
| Z Giraldo, David Andres (QA) | 14731 | 6
0
0
0
0
0
0
Groveland RNC Total | Total | 28360 | 13 | 2 | 1.3 | 32.5%
Kissimmee RNC
| Z Torres, David (QA) | 50196 | 19
| Z Curtis, Johnson (QA) | 47475 | 15
| Z Inderjit, Avinash (QA) | 8914 | 3
0
0
Kissimmee RNC Total | Total | 106585 | 37 | 3 | 2.4667 | 61.67%
Melbourne RNC
| Z Echevarria (QA) | 7956 | 4
| Z Long, Jordan (QA) | 2725 | 1
| Z Baird, Chris (QA) | 5193 | 2
0
0
Melbourne RNC | Total | 15874 | 7 | 3 | 0.46667 | 11.67%
N Jacksonville RNC
| Z Donald, Russ (QA) | 29574 | 11
| Z Corey, Blake (QA) | 8135 | 4
0
0
0
N Jacksonville RNC Total | Total | 37709 | 15 | 2 | 1.5 | 37.5%
Ocala RNC
| Z Scarberry, Dana (QA) | 8532 | 4
0
0
0
0
Ocala RNC Total | Total | 8532 | 4 | 1 | 0.8 | 20%
Port St Lucie RNC
| Z Clemmons, Marshannon (QA) | 13538 | 6
| Z Berkoben, Jason (QA) | 19002 | 11
0
0
0
Port St Lucie RNC Total | Total | 32540 | 17 | 2 | 1.7 | 42.5%
S Jacksonville RNC
| Z Donald, Russ (QA) | 29574 | 2
| Z Page, Terry (QA) | 35349 | 16
0
0
0
S Jacksonville RNC Total | Total | 64923 | 18 | 2 | 1.8 | 45%
Sanford RNC
| Z Greene, Matthew (QA) | 28008 | 11
| Z Browning, Scott (QA) | 19678 | 8
| Z Morrill, Christopher (QA) | 40134 | 19
| Z Czerniawski, Joseph (QA) | 27729 | 10
| Z Curry, Darryl (QA) | 30394 | 14
0
0
0
0
0
0
0
Sanford RNC Total | Total | 145943 | 62 | 5 | 2.48 | 62%
St Cloud RNC
| Z Harris, James (QA) | 56106 | 25
| Z Rivera, Wylmer (QA) | 10174 | 5
| Z Santos, Juan (QA) | 17617 | 9
0
0
0
0
St Cloud RNC Total | Total | 83897 | 39 | 3 | 2.6 | 65%
Tampa RNC
| Z McCord, Michael (QA) | 34003 | 13
| Z Perez, Yanier (QA) | 19683 | 9
| Z Vega, Mike (QA) | 14139 | 2
| Z Baboolal, Gayah (QA) | 27069 | 12
0
0
0
0
0
0
Tampa RNC Total | Total | 94894 | 36 | 4 | 1.8 | 45%
Venice RNC
| z Stilwell, Jerrold (QA) | 4217 | 2
| Z Diehl, Peter (QA) | 12100 | 6
| Z Nichols, John (Butch) (QA) | 13134 | 8
0
0
0
0
0
Venice RNC Total | Total | 29451 | 16 | 3 | 1.0667 | 26.67%
Winter Garden RNC
| Z Jeantilhomme, Charite (QA) | 32294 | 10
| Z - Taveras, Marino (QA) | 24490 | 10
| Z Johnson, Paul (QA) | 61877 | 22
0
0
0
0
0
0
Winter Garden RNC Total | Total | 118661 | 42 | 3 | 2.8 | 70%
Multi-Family
| Z Ramdeen (QA) | 32999 | 17
| Z Casas, Mauricio (QA) | 9375 | 5
0
0
0
0
0
Multi-Family | Total | 42374 | 22 | 2 | 2.2 | 55%
Grand Total | Total | 1018394 | 425 | 46 | 1.8478 | 46.2%

## Supervisor Rough QA
[7 empty] | TUG | TUG |  | Target | 20 | LastRow | 148
[5 empty] | Weeks |  |  | UG | Rough QA
Count of Type Of Work |  |  |  |  | 1 |  |  | T-Pole
Office | Rough_QA |  | Total | # active Supervisors | avg per week | % To Target 20
Auburndale RNC
0
0
0
0
0
0
0
0
0
0
Auburndale RNC Total | Total | 0 | 0 | 0
Brooksville RNC
0
0
0
0
0
0
0
0
0
Brooksville RNC Total | Total | 0 | 0 | 0
Daytona RNC
0
0
0
0
0
0
Daytona RNC Total | Total | 0 | 0 | 0
Ft Myers RNC
| ZZ Steyskal, Nathan Rough QA | 24253 | 12
0
0
0
0
0
0
0
Ft Myers RNC | Total | 24253 | 12 | 1 | 12 | 60%
Groveland RNC
0
0
0
0
0
0
0
0
Groveland RNC Total | Total | 0 | 0 | 0
Kissimmee RNC
| ZZ Pereira, Decio Rough QA | 25148 | 9
0
0
0
0
Kissimmee RNC Total | Total | 25148 | 9 | 1 | 9 | 45%
Melbourne RNC
| ZZ Sevcik, Eric ROUGH QA | 0 | 0
0
0
0
0
Melbourne RNC | Total | 0 | 0 | 1 | 0 | 0%
N Jacksonville RNC
| ZZ Monk, Adam Rough QA | 23158 | 11
0
0
0
0
N Jacksonville RNC Total | Total | 23158 | 11 | 1 | 11 | 55%
Ocala RNC
| ZZ John Seegers Rough QA | 22369 | 11
0
0
0
0
Ocala RNC Total | Total | 22369 | 11 | 1 | 11 | 55%
Port St Lucie RNC
0
0
0
0
0
Port St Lucie RNC Total | Total | 0 | 0 | 0
S Jacksonville RNC
0
0
0
0
0
S Jacksonville RNC Total | Total | 0 | 0 | 0
Sanford RNC
| ZZ Bogue, Brandon ROUGH QA | 33187 | 17
| ZZ Meier, Jeremy Rough QA | 6895 | 4
0
0
0
0
0
0
0
0
0
0
Sanford RNC Total | Total | 40082 | 21 | 2 | 10.5 | 52.5%
St Cloud RNC
| ZZ David De-Grasse Rough QA | 12185 | 7
0
0
0
0
0
0
St Cloud RNC Total | Total | 12185 | 7 | 1 | 7 | 35%
Tampa RNC
| ZZ Boucher, James ROUGH QA | 0 | 0
0
0
0
0
0
0
0
0
0
Tampa RNC Total | Total | 0 | 0 | 1 | 0 | 0%
Venice RNC
0
0
0
0
0
0
0
0
Venice RNC Total | Total | 0 | 0 | 0
Winter Garden RNC
| ZZ Robles, Jared Rough QA | 0 | 0
| ZZ Ellis, Berman Rough QA | 6790 | 2
0
0
0
0
0
0
0
Winter Garden RNC Total | Total | 6790 | 2 | 2 | 1 | 5%
Multi-Family
0
0
0
0
0
0
0
Multi-Family | Total | 0 | 0 | 0
Grand Total | Total | 153985 | 73 | 11 | 6.6364 | 33.18%

## Shop Productivity
|  |  | 1 weeks | 5 | 1202.0202
| Shop | Total Square ft. | crews | avg per crew | avg per day
1 | N Jacksonville RNC | 41198 | 7 | 5885.4286 | 1177.0857 | 97.93%
2 | Brooksville RNC | 56030 | 14 | 4002.1429 | 800.4286 | 66.59%
3 | Winter garden RNC | 58795 | 12 | 4899.5833 | 979.9167 | 81.52%
4 | Ocala RNC | 30459 | 6 | 5076.5 | 1015.3 | 84.47%
5 | S Jacksonville RNC | 57515 | 12 | 4792.9167 | 958.5833 | 79.75%
6 | Groveland RNC | 45219 | 9 | 5024.3333 | 1004.8667 | 83.6%
7 | Venice RNC | 40732 | 10 | 4073.2 | 814.64 | 67.77%
8 | Kissimmee RNC | 147384 | 21 | 7018.2857 | 1403.6571 | 116.8%
9 | Tampa RNC | 90654 | 17 | 5332.5882 | 1066.5176 | 88.73%
10 | St Cloud RNC | 104172 | 16 | 6510.75 | 1302.15 | 108.3%
11 | Auburndale RNC | 124750 | 20 | 6237.5 | 1247.5 | 103.8%
12 | Sanford RNC | 96897 | 21 | 4614.1429 | 922.8286 | 76.77%
13 | Daytona RNC | 50642 | 11 | 4603.8182 | 920.7636 | 76.6%
14 | Port St Lucie RNC | 41335 | 8 | 5166.875 | 1033.375 | 85.97%
15 | Ft Myers RNC | 30136 | 6 | 5022.6667 | 1004.5333 | 83.57%
16 | Melbourne RNC | 27823 | 5 | 5564.6 | 1112.92 | 92.59%
17 | Multi-Family | 21834 | 3 | 7278 | 1455.6 | 121.1%