## Productivity
[7 empty] | Previous week Productivity | YTD Productivity new tab |  | Week | Days |  |  |  |  | LastRow | 316
[10 empty] | 1 weeks | 5
Count of Type Of Work | TOTAL | 212 | 295 | 193 | 322 | 99 | 177 | 162 | 721541 | 144308.2 | 1207.3864
Office | Name | Rough QA | QA (Crew) | QA | TUT | Warranty | Rough | Trim | SQFT Production | SQFT per day | weight | SQFT to standard | Target | Emp 1st WO on this report | last WO on ytd report
S Jacksonville RNC | Larios Construction (Sub Labor) |  |  |  | 1 |  | 7 |  | 15686 | 3137.2 | 1000 | 5000 | 313.7% | 11/22/2019
Brooksville RNC | Green Electric (Brooksville) Sub Labor |  | 4 |  |  |  | 5 |  | 12046 | 2409.2 | 1000 | 5000 | 240.9% | 11/27/2019
Ft Myers RNC | James Cogley LLC (FT Myers Sub) | [5 empty] | 6 |  | 11000 | 2200 | 1000 | 5000 | 220% | 11/21/2019
Sanford RNC | Steven's Maintenance (Sub Labor) |  | 1 |  |  |  | 4 |  | 10544 | 2108.8 | 1000 | 5000 | 210.9% | 11/16/2019
Winter Garden RNC | Tulien, Fanes |  | 1 |  |  |  | 3 |  | 10520 | 2104 | 1000 | 5000 | 210.4% | 11/14/2019
Ft Myers RNC | Lucas Cirilo, Manuel |  |  |  | 5 |  | 5 |  | 10445 | 2089 | 1000 | 5000 | 208.9% | 11/27/2019
S Jacksonville RNC | Jason Brady |  | 1 |  |  |  |  | 6 | 13063 | 2612.6 | 1500 | 7500 | 174.2% | 11/27/2019
Brooksville RNC | JJANY (Brooksville) Sub Labor |  | 1 |  |  |  | 5 |  | 8358 | 1671.6 | 1000 | 5000 | 167.2% | 11/25/2019
Melbourne RNC | Fleming James | [6 empty] | 5 | 12217 | 2443.4 | 1500 | 7500 | 162.9% | 11/22/2019
Kissimmee RNC | Ayala Guzman | [5 empty] | 2 |  | 7579 | 1515.8 | 1000 | 5000 | 151.6% | 11/19/2019
Groveland RNC | Huggins, Gerardo | [6 empty] | 4 | 10605 | 2121 | 1500 | 7500 | 141.4% | 11/25/2019
Sanford RNC | Kelly (Sub Labor) | [6 empty] | 5 | 10544 | 2108.8 | 1500 | 7500 | 140.6% | 11/25/2019
Kissimmee RNC | Cesar, Dady | [5 empty] | 2 |  | 7000 | 1400 | 1000 | 5000 | 140% | 11/22/2019
Kissimmee RNC | Elias | [5 empty] | 2 |  | 6995 | 1399 | 1000 | 5000 | 139.9% | 11/19/2019
Kissimmee RNC | Guzman, Jonathan | [5 empty] | 2 |  | 6995 | 1399 | 1000 | 5000 | 139.9% | 11/27/2019
S Jacksonville RNC | Alex Reyes | [5 empty] | 3 |  | 6883 | 1376.6 | 1000 | 5000 | 137.7% | 11/25/2019
S Jacksonville RNC | Marshall Depreist (AP) | [5 empty] | 3 | 1 | 6573 | 1314.6 | 1000 | 5000 | 131.5% | 11/25/2019
Brooksville RNC | Wienke, Adam |  | 1 |  |  |  | 3 |  | 6550 | 1310 | 1000 | 5000 | 131% | 11/25/2019
Ft Myers RNC | Safford, Joe |  |  |  | 2 |  | 3 |  | 6102 | 1220.4 | 1000 | 5000 | 122% | 11/25/2019
Ocala RNC | Chris Barrett | [6 empty] | 4 | 9100 | 1820 | 1500 | 7500 | 121.3% | 11/21/2019
Groveland RNC | Cuba, Nerio |  |  | 4 |  |  |  | 5 | 8964 | 1792.8 | 1500 | 7500 | 119.5% | 11/25/2019
Venice RNC | Hanson, Travis | [6 empty] | 4 | 8802 | 1760.4 | 1500 | 7500 | 117.4% | 11/25/2019
Sanford RNC | BATC Sanford | [6 empty] | 5 | 8759 | 1751.8 | 1500 | 7500 | 116.8% | 11/25/2019
St Cloud RNC | Mollinedo, Darian | [5 empty] | 3 |  | 5733 | 1146.6 | 1000 | 5000 | 114.7% | 11/22/2019
S Jacksonville RNC | Steven Kennedy |  | 1 |  |  |  |  | 4 | 8575 | 1715 | 1500 | 7500 | 114.3% | 11/25/2019
Tampa RNC | Berice, Derius | [6 empty] | 4 | 7919 | 1583.8 | 1500 | 7500 | 105.6% | 11/25/2019
Sanford RNC | Edwards | [5 empty] | 1 | 2 | 6555 | 1311 | 1250 | 6250 | 104.9% | 11/26/2019
Venice RNC | Ponce, Adonis |  |  |  | 3 |  | 3 |  | 5129 | 1025.8 | 1000 | 5000 | 102.6% | 11/22/2019
Auburndale RNC | Camilo Ibar Services (sub Labor) | [5 empty] | 3 |  | 5112 | 1022.4 | 1000 | 5000 | 102.2% | 11/25/2019
Melbourne RNC | Sevcik, Eric | [5 empty] | 3 |  | 5016 | 1003.2 | 1000 | 5000 | 100.3% | 11/18/2019
Auburndale RNC | Torres,Jesus | [6 empty] | 4 | 7383 | 1476.6 | 1500 | 7500 | 98.44% | 11/22/2019
N Jacksonville RNC | Mcclough - Mcclough | [6 empty] | 3 | 7339 | 1467.8 | 1500 | 7500 | 97.85% | 11/22/2019
Kissimmee RNC | Cruz, Kevin | [6 empty] | 3 | 7023 | 1404.6 | 1500 | 7500 | 93.64% | 11/19/2019
Groveland RNC | Del Valle, Emanuel |  | 1 |  |  |  | 2 |  | 4622 | 924.4 | 1000 | 5000 | 92.44% | 11/20/2019
Kissimmee RNC | Vega, Antonio | [5 empty] | 1 | 1 | 5733 | 1146.6 | 1250 | 6250 | 91.73% | 11/13/2019
S Jacksonville RNC | Larios - Pancho (Sub Labor) |  |  |  | 8 |  | 2 |  | 4429 | 885.8 | 1000 | 5000 | 88.58% | 11/23/2019
Ocala RNC | Steven Maculewics | [5 empty] | 2 |  | 4353 | 870.6 | 1000 | 5000 | 87.06% | 11/22/2019
Daytona RNC | Stevenson | [6 empty] | 4 | 6473 | 1294.6 | 1500 | 7500 | 86.31% | 11/27/2019
Kissimmee RNC | Delaney Dennis | [5 empty] | 1 |  | 4304 | 860.8 | 1000 | 5000 | 86.08% | 11/15/2019
Daytona RNC | Kilpatrick | [5 empty] | 2 | 1 | 5344 | 1068.8 | 1250 | 6250 | 85.5% | 11/26/2019
N Jacksonville RNC | Aleksander Moroz | [5 empty] | 2 |  | 4247 | 849.4 | 1000 | 5000 | 84.94% | 11/25/2019
Tampa RNC | Bennett, Scott | [5 empty] | 2 |  | 4247 | 849.4 | 1000 | 5000 | 84.94% | 11/21/2019
Venice RNC | Santana, Yunior |  |  |  | 1 |  | 2 |  | 4243 | 848.6 | 1000 | 5000 | 84.86% | 11/22/2019
Tampa RNC | Delgado, Jose |  | 1 |  |  |  |  | 2 | 6311 | 1262.2 | 1500 | 7500 | 84.15% | 11/25/2019
St Cloud RNC | Rivera Nelson | [6 empty] | 3 | 6292 | 1258.4 | 1500 | 7500 | 83.89% | 11/21/2019
St Cloud RNC | Castaldi Joseph | [6 empty] | 3 | 6169 | 1233.8 | 1500 | 7500 | 82.25% | 11/25/2019
Venice RNC | Cabrera, Ramon |  |  |  | 1 |  | 2 |  | 4090 | 818 | 1000 | 5000 | 81.8% | 11/25/2019
St Cloud RNC | Carranza Pierre | [6 empty] | 3 | 6126 | 1225.2 | 1500 | 7500 | 81.68% | 11/22/2019
Sanford RNC | Nelms Dynasty (sub Labor) | [5 empty] | 1 |  | 4075 | 815 | 1000 | 5000 | 81.5% | 11/21/2019
Tampa RNC | McClosky, Tom | [5 empty] | 2 |  | 4038 | 807.6 | 1000 | 5000 | 80.76% | 11/25/2019
Venice RNC | Kendrick, Jereme |  |  |  | 1 |  | 2 |  | 4018 | 803.6 | 1000 | 5000 | 80.36% | 11/27/2019
Auburndale RNC | Acevedo, Jorge | [5 empty] | 2 |  | 3936 | 787.2 | 1000 | 5000 | 78.72% | 11/25/2019
Daytona RNC | Pierce_P |  | 2 |  |  |  | 2 |  | 3798 | 759.6 | 1000 | 5000 | 75.96% | 11/25/2019
Venice RNC | Given,James Jr | [6 empty] | 3 | 5680 | 1136 | 1500 | 7500 | 75.73% | 11/26/2019
S Jacksonville RNC | Daniel Wilkinson | [5 empty] | 2 |  | 3738 | 747.6 | 1000 | 5000 | 74.76% | 11/21/2019
Kissimmee RNC | Torres,Luis | [5 empty] | 2 |  | 3721 | 744.2 | 1000 | 5000 | 74.42% | 11/21/2019
Auburndale RNC | Diaz, Yidiel | [6 empty] | 3 | 5384 | 1076.8 | 1500 | 7500 | 71.79% | 11/21/2019
Sanford RNC | Crespo | [5 empty] | 2 |  | 3577 | 715.4 | 1000 | 5000 | 71.54% | 11/22/2019
Daytona RNC | Carter | [5 empty] | 2 |  | 3576 | 715.2 | 1000 | 5000 | 71.52% | 11/21/2019
Sanford RNC | North Orlando Training Crew |  | 1 |  |  |  |  | 3 | 5364 | 1072.8 | 1500 | 7500 | 71.52% | 11/22/2019
Winter Garden RNC | Aponte, Felipe |  | 4 |  |  |  |  | 2 | 5354 | 1070.8 | 1500 | 7500 | 71.39% | 11/25/2019
Auburndale RNC | Adkins,Charles | [6 empty] | 3 | 5353 | 1070.6 | 1500 | 7500 | 71.37% | 11/26/2019
N Jacksonville RNC | Boucher, Mathew Eugene |  | 1 |  |  |  | 1 | 1 | 4459 | 891.8 | 1250 | 6250 | 71.34% | 11/21/2019
S Jacksonville RNC | Kirk Thomer | [5 empty] | 1 | 1 | 4434 | 886.8 | 1250 | 6250 | 70.94% | 11/25/2019
Tampa RNC | Ramos, Jose |  | 1 |  |  |  | 2 |  | 3533 | 706.6 | 1000 | 5000 | 70.66% | 11/22/2019
Auburndale RNC | Eodice, Cody | [5 empty] | 2 |  | 3420 | 684 | 1000 | 5000 | 68.4% | 11/26/2019
Ocala RNC | Switzer, Justin | [5 empty] | 1 | 1 | 4207 | 841.4 | 1250 | 6250 | 67.31% | 11/20/2019
Kissimmee RNC | Aguayo, Antonio |  | 1 |  |  |  | 1 |  | 3353 | 670.6 | 1000 | 5000 | 67.06% | 11/25/2019
Kissimmee RNC | Annulysse, Jean | [5 empty] | 1 |  | 3348 | 669.6 | 1000 | 5000 | 66.96% | 11/22/2019
Auburndale RNC | Pace, Melvin | [6 empty] | 3 | 4986 | 997.2 | 1500 | 7500 | 66.48% | 11/22/2019
Auburndale RNC | Pedraza Gonzalez, Rafael | [6 empty] | 2 | 4946 | 989.2 | 1500 | 7500 | 65.95% | 11/26/2019
Sanford RNC | AP Elswoth Busano | [5 empty] | 1 |  | 3291 | 658.2 | 1000 | 5000 | 65.82% | 11/19/2019
Tampa RNC | Pineda, Noel | [6 empty] | 3 | 4931 | 986.2 | 1500 | 7500 | 65.75% | 11/25/2019
S Jacksonville RNC | Darren Ferrell | [6 empty] | 2 | 4874 | 974.8 | 1500 | 7500 | 64.99% | 11/22/2019
St Cloud RNC | South Orlando Training Crew |  | 5 |  |  |  | 2 |  | 3187 | 637.4 | 1000 | 5000 | 63.74% | 11/20/2019
N Jacksonville RNC | Evan Wagner LLC | [5 empty] | 1 |  | 3143 | 628.6 | 1000 | 5000 | 62.86% | 11/18/2019
Port St Lucie RNC | Whyte | [5 empty] | 1 |  | 3130 | 626 | 1000 | 5000 | 62.6% | 11/26/2019
Tampa RNC | Laura, Patrick | [6 empty] | 2 | 4662 | 932.4 | 1500 | 7500 | 62.16% | 11/22/2019
Winter Garden RNC | Valverde, Armando |  | 3 |  |  |  |  | 1 | 4645 | 929 | 1500 | 7500 | 61.93% | 11/26/2019
Ocala RNC | Devin Dickinson |  |  |  | 2 |  | 2 |  | 3088 | 617.6 | 1000 | 5000 | 61.76% | 11/20/2019
Ft Myers RNC | Allen, Sean |  | 1 |  |  |  |  | 3 | 4557 | 911.4 | 1500 | 7500 | 60.76% | 11/21/2019
Groveland RNC | Quinones, Ray Jr |  | 1 |  |  |  | 1 | 1 | 3778 | 755.6 | 1250 | 6250 | 60.45% | 11/27/2019
Venice RNC | Cadet, Paul |  |  |  | 2 |  | 2 |  | 3018 | 603.6 | 1000 | 5000 | 60.36% | 11/27/2019
Daytona RNC | AP Stramondo | [5 empty] | 2 |  | 3009 | 601.8 | 1000 | 5000 | 60.18% | 11/27/2019
Auburndale RNC | Mario Bargaineer | [5 empty] | 1 |  | 2902 | 580.4 | 1000 | 5000 | 58.04% | 11/21/2019
Daytona RNC | Carcano | [6 empty] | 2 | 4340 | 868 | 1500 | 7500 | 57.87% | 11/22/2019
Winter Garden RNC | Espanga, Derosema | [5 empty] | 1 |  | 2866 | 573.2 | 1000 | 5000 | 57.32% | 11/19/2019
Tampa RNC | Williams, Charlie JR (Dad) | [5 empty] | 1 |  | 2855 | 571 | 1000 | 5000 | 57.1% | 11/21/2019
Groveland RNC | Morocho, Danny |  | 1 |  |  |  | 1 |  | 2777 | 555.4 | 1000 | 5000 | 55.54% | 11/26/2019
St Cloud RNC | Locorini, Jason | [5 empty] | 1 | 1 | 3470 | 694 | 1250 | 6250 | 55.52% | 11/25/2019
Melbourne RNC | Webster, Garrett | 1 |  |  |  |  | 1 |  | 2725 | 545 | 1000 | 5000 | 54.5% | 11/20/2019
Auburndale RNC | Vega, Ramon | [6 empty] | 2 | 4006 | 801.2 | 1500 | 7500 | 53.41% | 11/21/2019
Brooksville RNC | Tirado, Omar | [5 empty] | 1 |  | 2601 | 520.2 | 1000 | 5000 | 52.02% | 11/25/2019
Melbourne RNC | Soto, Nelson | [6 empty] | 2 | 3856 | 771.2 | 1500 | 7500 | 51.41% | 11/18/2019
Sanford RNC | Michael Lyng | [6 empty] | 2 | 3853 | 770.6 | 1500 | 7500 | 51.37% | 11/25/2019
Auburndale RNC | Camilo Ibar (Misael) | [5 empty] | 1 |  | 2566 | 513.2 | 1000 | 5000 | 51.32% | 11/22/2019
Groveland RNC | Delgado, Jesus |  | 1 |  |  |  | 1 |  | 2566 | 513.2 | 1000 | 5000 | 51.32% | 11/26/2019
Melbourne RNC | Oneal, Tracy |  | 2 |  |  |  | 1 |  | 2566 | 513.2 | 1000 | 5000 | 51.32% | 11/27/2019
Melbourne RNC | Gonzalez, Girardo | [5 empty] | 1 |  | 2566 | 513.2 | 1000 | 5000 | 51.32% | 11/18/2019
Winter Garden RNC | Ponce, Jose |  |  |  |  | 1 |  | 1 | 3812 | 762.4 | 1500 | 7500 | 50.83% | 11/27/2019
S Jacksonville RNC | Nathan Hardy |  | 1 |  |  |  | 1 |  | 2511 | 502.2 | 1000 | 5000 | 50.22% | 11/26/2019
Daytona RNC | Copeland | [6 empty] | 2 | 3766 | 753.2 | 1500 | 7500 | 50.21% | 11/25/2019
Port St Lucie RNC | Buell | [5 empty] | 1 |  | 2506 | 501.2 | 1000 | 5000 | 50.12% | 11/26/2019
Port St Lucie RNC | Mitchell Munroe | [5 empty] | 1 |  | 2506 | 501.2 | 1000 | 5000 | 50.12% | 11/26/2019
St Cloud RNC | Chicoye Sadrak | [6 empty] | 2 | 3724 | 744.8 | 1500 | 7500 | 49.65% | 11/26/2019
Port St Lucie RNC | Sherba | [6 empty] | 2 | 3722 | 744.4 | 1500 | 7500 | 49.63% | 11/26/2019
Brooksville RNC | Moats, Clint | [5 empty] | 1 |  | 2470 | 494 | 1000 | 5000 | 49.4% | 11/25/2019
Sanford RNC | Austin, James | [5 empty] | 1 |  | 2455 | 491 | 1000 | 5000 | 49.1% | 11/21/2019
Brooksville RNC | Concepcion, Moises | [6 empty] | 2 | 3677 | 735.4 | 1500 | 7500 | 49.03% | 11/25/2019
Winter Garden RNC | Pirela, Carlos | [6 empty] | 1 | 3652 | 730.4 | 1500 | 7500 | 48.69% | 11/25/2019
N Jacksonville RNC | Alexander Pecherin | [6 empty] | 2 | 3626 | 725.2 | 1500 | 7500 | 48.35% | 11/22/2019
St Cloud RNC | Morales, Walter | [6 empty] | 2 | 3527 | 705.4 | 1500 | 7500 | 47.03% | 11/25/2019
Groveland RNC | Perez, Edmundo | [5 empty] | 1 |  | 2327 | 465.4 | 1000 | 5000 | 46.54% | 11/22/2019
Ft Myers RNC | Montejo, Maria |  | 2 |  |  |  | 1 |  | 2255 | 451 | 1000 | 5000 | 45.1% | 10/22/2019
Tampa RNC | Rodriguez, Emilio | [5 empty] | 1 |  | 2233 | 446.6 | 1000 | 5000 | 44.66% | 11/25/2019
Tampa RNC | Boyd, Dave | [5 empty] | 1 |  | 2196 | 439.2 | 1000 | 5000 | 43.92% | 11/22/2019
Kissimmee RNC | Olivero, Moises Concepcion | [6 empty] | 2 | 3247 | 649.4 | 1500 | 7500 | 43.29% | 11/18/2019
Brooksville RNC | Edward Huntoon | [5 empty] | 1 |  | 2121 | 424.2 | 1000 | 5000 | 42.42% | 11/19/2019
Auburndale RNC | Hartley, Thomas |  | 1 |  |  |  | 1 |  | 2109 | 421.8 | 1000 | 5000 | 42.18% | 11/27/2019
Auburndale RNC | Francisco Torres | [5 empty] | 1 |  | 2109 | 421.8 | 1000 | 5000 | 42.18% | 11/21/2019
Auburndale RNC | Mojica,Eddie | [5 empty] | 1 |  | 2063 | 412.6 | 1000 | 5000 | 41.26% | 11/21/2019
Tampa RNC | Alfonso, Jose | [6 empty] | 2 | 3094 | 618.8 | 1500 | 7500 | 41.25% | 11/22/2019
Tampa RNC | Rojas, Yarian | [5 empty] | 1 |  | 2060 | 412 | 1000 | 5000 | 41.2% | 11/19/2019
Groveland RNC | Christie, Norman | [5 empty] | 1 |  | 2034 | 406.8 | 1000 | 5000 | 40.68% | 11/20/2019
Groveland RNC | Reynoso, Ramon |  | 2 |  |  |  | 1 |  | 2021 | 404.2 | 1000 | 5000 | 40.42% | 11/21/2019
Multi-Family | 4954 Maintenance (Sub Labor) | [6 empty] | 1 | 3014 | 602.8 | 1500 | 7500 | 40.19% | 11/21/2019
Tampa RNC | Gonzalez, Francisco | [5 empty] | 1 |  | 2003 | 400.6 | 1000 | 5000 | 40.06% | 11/22/2019
Kissimmee RNC | Vega,Giovanni | [5 empty] | 1 |  | 1960 | 392 | 1000 | 5000 | 39.2% | 11/19/2019
St Cloud RNC | Rojas, David |  | 1 |  |  |  | 1 |  | 1933 | 386.6 | 1000 | 5000 | 38.66% | 11/20/2019
St Cloud RNC | Rojas, Axel | [5 empty] | 1 |  | 1896 | 379.2 | 1000 | 5000 | 37.92% | 11/25/2019
Brooksville RNC | West, Matthew | [5 empty] | 1 |  | 1876 | 375.2 | 1000 | 5000 | 37.52% | 11/25/2019
St Cloud RNC | Leca Jonathan | [6 empty] | 1 | 2809 | 561.8 | 1500 | 7500 | 37.45% | 11/23/2019
Daytona RNC | Connolly | [5 empty] | 1 |  | 1867 | 373.4 | 1000 | 5000 | 37.34% | 11/21/2019
N Jacksonville RNC | Travis Brown |  | 1 |  |  |  | 1 |  | 1862 | 372.4 | 1000 | 5000 | 37.24% | 11/25/2019
St Cloud RNC | Sandoval Luis |  | 1 |  |  |  | 1 |  | 1855 | 371 | 1000 | 5000 | 37.1% | 11/20/2019
Brooksville RNC | Ruiz, Yamel | [6 empty] | 1 | 2756 | 551.2 | 1500 | 7500 | 36.75% | 11/26/2019
Auburndale RNC | Tampa Training Crew | [5 empty] | 1 |  | 1828 | 365.6 | 1000 | 5000 | 36.56% | 11/20/2019
Brooksville RNC | Dwelly,Seth |  | 5 |  |  |  | 1 |  | 1828 | 365.6 | 1000 | 5000 | 36.56% | 11/26/2019
Tampa RNC | Ramirez,Marco |  | 2 |  |  |  | 1 |  | 1828 | 365.6 | 1000 | 5000 | 36.56% | 11/25/2019
St Cloud RNC | Vasquez Jose | [6 empty] | 1 | 2644 | 528.8 | 1500 | 7500 | 35.25% | 11/25/2019
Kissimmee RNC | Francisco Reccy De Leon | [5 empty] | 1 |  | 1732 | 346.4 | 1000 | 5000 | 34.64% | 11/21/2019
Tampa RNC | Gomez, Eulalio | [5 empty] | 1 |  | 1726 | 345.2 | 1000 | 5000 | 34.52% | 11/26/2019
Auburndale RNC | Z Maxson, Damien (QA) |  | 7 | 10 |  |  |  | 1 | 2570 | 514 | 1500 | 7500 | 34.27% | 11/27/2019
Auburndale RNC | Wolf, David | [5 empty] | 1 |  | 1707 | 341.4 | 1000 | 5000 | 34.14% | 11/21/2019
Port St Lucie RNC | Wymer | [5 empty] | 1 |  | 1689 | 337.8 | 1000 | 5000 | 33.78% | 11/25/2019
Tampa RNC | Annicaro, Thomas | [5 empty] | 1 |  | 1673 | 334.6 | 1000 | 5000 | 33.46% | 11/22/2019
Ocala RNC | Roberto Munoz | [5 empty] | 1 |  | 1672 | 334.4 | 1000 | 5000 | 33.44% | 11/20/2019
Sanford RNC | Silverstein |  | 1 |  |  |  | 1 |  | 1672 | 334.4 | 1000 | 5000 | 33.44% | 11/26/2019
St Cloud RNC | Rivera Robert |  | 1 |  |  |  | 1 |  | 1637 | 327.4 | 1000 | 5000 | 32.74% | 11/20/2019
Auburndale RNC | Mercado, Alexander | [6 empty] | 1 | 2410 | 482 | 1500 | 7500 | 32.13% | 11/25/2019
Auburndale RNC | Luis Montada | [6 empty] | 1 | 2380 | 476 | 1500 | 7500 | 31.73% | 11/25/2019
Winter Garden RNC | Algarin, Joel |  | 2 |  |  |  |  | 1 | 2350 | 470 | 1500 | 7500 | 31.33% | 11/26/2019
Auburndale RNC | Camilo Ibar (Alberto) | [5 empty] | 1 |  | 1554 | 310.8 | 1000 | 5000 | 31.08% | 11/22/2019
Daytona RNC | Seraphin Antoine | [5 empty] | 1 |  | 1546 | 309.2 | 1000 | 5000 | 30.92% | 11/25/2019
Sanford RNC | Tanner | [6 empty] | 1 | 2317 | 463.4 | 1500 | 7500 | 30.89% | 11/21/2019
Ocala RNC | Jules Etienne |  |  |  | 1 |  | 1 |  | 1544 | 308.8 | 1000 | 5000 | 30.88% | 11/22/2019
Auburndale RNC | Griffin, Nathan | [5 empty] | 1 |  | 1532 | 306.4 | 1000 | 5000 | 30.64% | 11/22/2019
Ocala RNC | Jonathan Lopez | [5 empty] | 1 |  | 1504 | 300.8 | 1000 | 5000 | 30.08% | 11/22/2019
Sanford RNC | Anes, Roberto | [6 empty] | 1 | 2247 | 449.4 | 1500 | 7500 | 29.96% | 11/21/2019
N Jacksonville RNC | Y Brent Blair (TUT) |  | 6 |  | 5 |  | 1 |  | 1490 | 298 | 1000 | 5000 | 29.8% | 11/25/2019
St Cloud RNC | Jackson Trelon | [5 empty] | 1 |  | 1449 | 289.8 | 1000 | 5000 | 28.98% | 11/20/2019
Tampa RNC | Moreira Gonzalez, Lixander | [6 empty] | 1 | 2045 | 409 | 1500 | 7500 | 27.27% | 11/26/2019
Sanford RNC | Ramirez | [6 empty] | 1 | 2034 | 406.8 | 1500 | 7500 | 27.12% | 11/20/2019
Venice RNC | Sprague, Alec |  | 2 |  | 2 |  |  | 1 | 2003 | 400.6 | 1500 | 7500 | 26.71% | 11/25/2019
St Cloud RNC | Peterson, Rodrick | [6 empty] | 1 | 1966 | 393.2 | 1500 | 7500 | 26.21% | 11/21/2019
Port St Lucie RNC | Yepez | [6 empty] | 1 | 1951 | 390.2 | 1500 | 7500 | 26.01% | 11/22/2019
Port St Lucie RNC | Johnston | [6 empty] | 1 | 1876 | 375.2 | 1500 | 7500 | 25.01% | 11/25/2019
Auburndale RNC | Rivera, Miguel | [6 empty] | 1 | 1853 | 370.6 | 1500 | 7500 | 24.71% | 11/22/2019
Sanford RNC | Bassett |  |  |  | 1 |  |  | 1 | 1828 | 365.6 | 1500 | 7500 | 24.37% | 11/22/2019
St Cloud RNC | Passwaters, Talen | [6 empty] | 1 | 1699 | 339.8 | 1500 | 7500 | 22.65% | 11/21/2019
Brooksville RNC | Diaz,Delia | [6 empty] | 1 | 1673 | 334.6 | 1500 | 7500 | 22.31% | 11/25/2019
Brooksville RNC | Y Gonzalez, Joan (TUT) |  |  |  | 12 |  |  | 1 | 1672 | 334.4 | 1500 | 7500 | 22.29% | 11/26/2019
Ft Myers RNC | Breese, Jonathan |  | 2 |  |  |  |  | 1 | 1672 | 334.4 | 1500 | 7500 | 22.29% | 11/27/2019
Service ORL | Lynn, Revels | [6 empty] | 1 | 1672 | 334.4 | 1500 | 7500 | 22.29% | 11/25/2019
Service ORL | Brian, Hock | [6 empty] | 1 | 1672 | 334.4 | 1500 | 7500 | 22.29% | 11/22/2019
Ft Myers RNC | Fabergas, Rolando |  | 2 |  |  |  |  | 1 | 1519 | 303.8 | 1500 | 7500 | 20.25% | 11/21/2019
Auburndale RNC | ZZ Ramirez, Frank Rough QA | 14 | 1 | [10 empty] | 11/25/2019
Auburndale RNC | Z Rivera, Corey (QA) |  | 10 | 10 | [9 empty] | 11/26/2019
Auburndale RNC | Y Blue, Ricky (TUT) |  | 2 |  | 20 | [8 empty] | 11/25/2019
Auburndale RNC | ZZ Adkins, Scott Rough QA | 7 | [11 empty] | 11/25/2019
Auburndale RNC | Z Dickinson, Marvin (QA) |  |  |  |  | 6 | [7 empty] | 11/26/2019
Auburndale RNC | ZZ Strickler, Alan Rough QA | 12 | [11 empty] | 11/25/2019
Auburndale RNC | Z Christian, Paul (QA) |  | 5 | 9 | [9 empty] | 11/25/2019
Auburndale RNC | Z Owen, Kevin (QA) |  | 1 |  |  | 3 | [7 empty] | 11/25/2019
Auburndale RNC | Y Beoto, Juan (TUT) |  |  |  | 15 | [8 empty] | 11/26/2019
Auburndale RNC | Y Morales, Jose (TUT) |  |  |  | 22 | [8 empty] | 11/26/2019
Brooksville RNC | ZZ Concepcion, Gladdys ROUGH QA | 11 | [11 empty] | 11/26/2019
Brooksville RNC | Z Leal, Wilmer (QA) |  | 5 | 1 |  | 2 | [7 empty] | 11/26/2019
Brooksville RNC | ZZ Hooker, Freddie ROUGH QA | 11 | [11 empty] | 11/25/2019
Brooksville RNC | ZZ Murch, Robert ROUGH QA | 9 | [11 empty] | 11/27/2019
Brooksville RNC | Z Vega, Mike (QA) |  | 4 | 1 |  | 2 | [7 empty] | 11/26/2019
Brooksville RNC | Y Fortner, Russell (TUT) |  | 10 |  | 17 | [8 empty] | 11/25/2019
Brooksville RNC | Keys, Michael |  | 1 | [10 empty] | 11/25/2019
Brooksville RNC | McElvain, Patrick |  | 1 | [10 empty] | 11/25/2019
Brooksville RNC | Y Whiting, Michael (TUT) |  |  |  | 2 | [8 empty] | 11/25/2019
Daytona RNC | ZZ Dean, Phillip ROUGH QA | 7 | [11 empty] | 11/26/2019
Daytona RNC | ZZ Bowers, Zachary ROUGH QA | 6 | 1 | [10 empty] | 11/25/2019
Daytona RNC | Z Waggoner, Nathaniel (QA) |  | 9 | 1 |  | 2 | [7 empty] | 11/26/2019
Daytona RNC | Y DeWitt, Brett (TUT) |  |  |  | 11 | [8 empty] | 11/26/2019
Daytona RNC | Y Whitaker, Christopher (TUT) |  |  |  | 15 | [8 empty] | 11/27/2019
Daytona RNC | Z Moussette, Frank (QA) |  | 2 | 9 |  | 4 | [7 empty] | 11/25/2019
Ft Myers RNC | Z Duran, Eudy (QA) | 1 | [11 empty] | 11/18/2019
Ft Myers RNC | ZZ Steyskal, Nathan Rough QA |  |  | 2 | [9 empty] | 11/15/2019
Ft Myers RNC | Y Wade, Antonio (TUT) |  |  |  | 4 | [8 empty] | 11/25/2019
Groveland RNC | ZZ Aleman, Felix Rough QA | 2 | [11 empty] | 11/27/2019
Groveland RNC | Z Nunez, Julio (QA) | 1 |  | 20 |  | 3 | [7 empty] | 11/22/2019
Groveland RNC | Y Silguero, Ricardo (TUT) |  |  |  | 26 | [8 empty] | 11/27/2019
Groveland RNC | ZZ Herrera, Alvaro Rough QA | 8 | [11 empty] | 11/30/2019
Groveland RNC | Z Giraldo, David Andres (QA) |  | 7 | 6 | [9 empty] | 11/22/2019
Groveland RNC | ZZ Thomas, Michael Rough QA | 1 | [11 empty] | 11/25/2019
Groveland RNC | Z Ibarra, Rigoberto (QA) |  | 8 | 6 |  | 1 | [7 empty] | 11/25/2019
Kissimmee RNC | Z Torres, David (QA) |  |  | 3 | [9 empty] | 11/18/2019
Kissimmee RNC | Diaz, Jorge | [12 empty] | 11/14/2019
Kissimmee RNC | Z Camacho, Andre (QA) |  |  | 1 | [9 empty] | 11/15/2019
Kissimmee RNC | ZZ Guzman, Lisandro Rough QA | 11 | [11 empty] | 11/15/2019
Kissimmee RNC | Z Curtis, Johnson (QA) |  |  |  |  | 6 | [7 empty] | 11/26/2019
Kissimmee RNC | Z Inderjit, Avinash (QA) |  |  | 17 | [9 empty] | 11/12/2019
Kissimmee RNC | AP Javier Lopez |  | 1 | [10 empty] | 11/21/2019
Kissimmee RNC | Eric Harmon |  | 2 | [10 empty] | 11/26/2019
Melbourne RNC | Richey, Kyle |  | 4 | [10 empty] | 11/07/2019
Melbourne RNC | ZZ Long, Jordan (ROUGH QA) | 1 |  | 2 | [9 empty] | 11/22/2019
Melbourne RNC | Z Dean, Art (QA) |  | 6 | 3 |  | 1 | [7 empty] | 11/26/2019
Melbourne RNC | Z Baird, Chris (QA) |  | 8 |  | 7 | 1 | [7 empty] | 11/26/2019
Melbourne RNC | ZZ Rogers, Mike (ROUGH QA) | 1 |  |  | 1 | [8 empty] | 11/22/2019
Multi-Family | Green Electric Pro Sub Crew | [12 empty] | 11/25/2019
Multi-Family | Z Ramdeen (QA) |  |  | 1 |  | 3 | [7 empty] | 11/27/2019
Multi-Family | Z Casas, Mauricio (QA) |  |  |  |  | 4 | [7 empty] | 11/25/2019
Multi-Family | Felix Louis Santiago Jr | [12 empty] | 11/21/2019
N Jacksonville RNC | Z Donald, Russ (QA) |  | 12 | 4 | [9 empty] | 11/26/2019
N Jacksonville RNC | ZZ Monk, Adam Rough QA | 4 | [11 empty] | 11/26/2019
N Jacksonville RNC | Z Corey, Blake (QA) |  | 7 | 7 |  | 3 | [7 empty] | 11/26/2019
Ocala RNC | ZZ Boucher, James ROUGH QA | 9 | [11 empty] | 11/26/2019
Ocala RNC | Z Scarberry, Dana (QA) |  | 7 | 1 |  | 1 | [7 empty] | 11/26/2019
Ocala RNC | Y Marshall, Dillan (TUT) |  | 6 |  | 12 | [8 empty] | 11/22/2019
Port St Lucie RNC | Z Clemmons, Marshannon (QA) |  | 12 | 1 |  | 1 | [7 empty] | 11/25/2019
Port St Lucie RNC | ZZ Perlmutter, Mark ROUGH QA | 3 | [11 empty] | 11/27/2019
Port St Lucie RNC | Z Berkoben, Jason (QA) |  | 12 | 1 |  | 1 | [7 empty] | 11/26/2019
S Jacksonville RNC | Smith | [12 empty] | 11/20/2019
S Jacksonville RNC | Z Welker, Daniel (QA) |  | 4 |  |  | 4 | [7 empty] | 11/26/2019
S Jacksonville RNC | ZZ Rose, Geno Rough QA | 7 | [11 empty] | 11/25/2019
S Jacksonville RNC | ZZ Otis, Ditannon Rough QA | 11 | 2 | [10 empty] | 11/25/2019
S Jacksonville RNC | Z Page, Terry (QA) |  | 2 | 6 |  | 2 | [7 empty] | 11/26/2019
S Jacksonville RNC | Y Baltazar, Abimael (TUT) |  | 7 |  | 18 | [8 empty] | 11/26/2019
Sanford RNC | Spicer |  |  | 4 | 2 | [8 empty] | 11/15/2019
Sanford RNC | Z Greene, Matthew (QA) |  | 1 | 4 | 2 | 3 | [7 empty] | 11/25/2019
Sanford RNC | Z Browning, Scott (QA) |  |  |  |  | 3 | [7 empty] | 11/25/2019
Sanford RNC | Z Morrill, Christopher (QA) | 1 |  |  | 2 | 3 | [7 empty] | 11/26/2019
Sanford RNC | Fleming |  | 2 | [10 empty] | 11/25/2019
Sanford RNC | Z Czerniawski, Joseph (QA) |  |  | 3 | [9 empty] | 11/21/2019
Sanford RNC | ZZ Baker, Chris ROUGH QA | 5 |  |  | 1 | [8 empty] | 11/25/2019
Sanford RNC | ZZ Bogue, Brandon ROUGH QA | 6 |  |  | 1 | [8 empty] | 11/14/2019
Sanford RNC | ZZ Continanzi, James ROUGH QA | 5 | 1 | [10 empty] | 11/26/2019
Sanford RNC | ZZ Meier, Jeremy Rough QA |  |  | 3 |  | 1 | [7 empty] | 11/25/2019
Sanford RNC | Y Jose Santiago (TUT) |  | 1 |  | 11 | [8 empty] | 11/18/2019
Sanford RNC | AP William Pond |  | 1 | [10 empty] | 11/26/2019
Sanford RNC | Duxbury |  | 2 | [10 empty] | 11/26/2019
Sanford RNC | Z Curry, Darryl (QA) |  |  | 7 |  | 5 | [7 empty] | 11/22/2019
Sanford RNC | ZZ Ron Krueger Rough QA | 1 | [11 empty] | 11/25/2019
Sanford RNC | Y Jose Cruz (TUT) |  |  |  | 12 | [8 empty] | 11/18/2019
Sanford RNC | ZZ Ronald Krueger (Rough QA) | 9 | [11 empty] | 11/18/2019
Service ORL | John, Kopishke | [12 empty] | 11/25/2019
Service ORL | Gerald, Morgan | [12 empty] | 11/25/2019
St Cloud RNC | Y Jarvis, Michael (TUT) |  |  |  | 10 | [8 empty] | 11/18/2019
St Cloud RNC | Z Harris, James (QA) |  |  |  |  | 5 | [7 empty] | 11/26/2019
St Cloud RNC | Y Harf, Keith (TUT) |  |  |  | 3 | [8 empty] | 11/26/2019
St Cloud RNC | ZZ David De-Grasse Rough QA | 6 | [11 empty] | 11/19/2019
St Cloud RNC | Z Rivera, Wylmer (QA) |  |  | 4 |  | 3 | [7 empty] | 11/26/2019
St Cloud RNC | ZZ Liles, Isaac Rough QA | 3 | [11 empty] | 11/26/2019
St Cloud RNC | ZZ Leon, Humberto Rough QA | 4 | [11 empty] | 11/25/2019
St Cloud RNC | ZZ Leija, Diego Rough QA | 2 | [11 empty] | 11/27/2019
St Cloud RNC | Z Santos, Juan (QA) |  |  | 18 |  | 3 | [7 empty] | 11/25/2019
Tampa RNC | Y Cordovi, Carlos (TUT) |  | 3 |  | 6 | [8 empty] | 11/25/2019
Tampa RNC | Z McCord, Michael (QA) |  | 3 | 1 |  | 6 | [7 empty] | 11/26/2019
Tampa RNC | Y Cruz, Jalierky (TUT) |  |  |  | 17 | [8 empty] | 11/25/2019
Tampa RNC | Z Perez, Yanier (QA) |  |  | 3 |  | 2 | [7 empty] | 11/25/2019
Tampa RNC | ZZ Miguel Concepcion ROUGH QA | 3 |  | 3 | [9 empty] | 11/24/2019
Tampa RNC | ZZ Rodriguez, Eder ROUGH QA | 9 | [11 empty] | 11/25/2019
Tampa RNC | Z Baboolal, Gayah (QA) |  | 5 | 3 |  | 2 | [7 empty] | 11/26/2019
Tampa RNC | Pipe, Anthony |  | 1 | [10 empty] | 11/22/2019
Tampa RNC | Y Martin, Nick (TUT) |  | 1 |  | 4 | [8 empty] | 11/25/2019
Venice RNC | z Stilwell, Jerrold (QA) |  | 16 | 2 | 1 | 1 | [7 empty] | 11/25/2019
Venice RNC | Y Castaneda, Guadalupe (TUT) |  |  |  | 16 | [8 empty] | 11/25/2019
Venice RNC | Z Diehl, Peter (QA) |  | 3 | 3 |  | 1 | [7 empty] | 11/26/2019
Venice RNC | ZZ Palmucci, James ROUGH QA | 8 | [11 empty] | 11/25/2019
Venice RNC | ZZ Rodriguez, Pedro ROUGH QA | 6 |  | 1 | [9 empty] | 11/26/2019
Venice RNC | Z Nichols, John (Butch) (QA) |  | 4 | 4 |  | 2 | [7 empty] | 11/27/2019
Winter Garden RNC | Z Jeantilhomme, Charite (QA) |  | 1 | [10 empty] | 11/25/2019
Winter Garden RNC | Santiago, Edwin |  | 1 | [10 empty] | 11/27/2019
Winter Garden RNC | Del Valle, David |  | 2 | [10 empty] | 11/25/2019
Winter Garden RNC | Z - Taveras, Marino (QA) |  | 9 | 4 |  | 2 | [7 empty] | 11/25/2019
Winter Garden RNC | De Jesus, Pedro |  | 4 | [10 empty] | 11/25/2019
Winter Garden RNC | ZZ Alderman, Jody Rough QA | 4 | [11 empty] | 11/25/2019
Winter Garden RNC | ZZ Ellis, Berman Rough QA | 2 | [11 empty] | 11/26/2019
Winter Garden RNC | Y - Jackson, Amechi (TUT) |  |  |  | 17 | [8 empty] | 11/27/2019
Winter Garden RNC | Z Johnson, Paul (QA) |  |  |  |  | 6 | [7 empty] | 11/25/2019

## TUT Report
[6 empty] | TUG | TUG | LastRow | 83
UG
Count of Type Of Work |  |  | 3 |  |  |  | T-Pole
Office | Crew | Total | # active tuts | avg per Day | % To Target 35
Auburndale RNC
| Y Blue, Ricky (TUT) | 20
| Y Beoto, Juan (TUT) | 15
| Y Morales, Jose (TUT) | 22
0
0
Auburndale RNC Total |  | 57 | 3 | 3.8 | 54.29%
Brooksville RNC
| Y Gonzalez, Joan (TUT) | 12
| Y Fortner, Russell (TUT) | 17
| Y Whiting, Michael (TUT) | 2
0
0
Brooksville RNC Total |  | 31 | 3 | 2.0667 | 29.52%
Daytona RNC
| Y DeWitt, Brett (TUT) | 11
| Y Whitaker, Christopher (TUT) | 15
0
0
0
Daytona RNC Total |  | 26 | 2 | 2.6 | 37.14%
FT Myers RNC
| Y Jose Cruz (TUT) | 0
0
0
0
0
FT Myers RNC |  | 0 | 1 | 0 | 0%
Groveland RNC
| Y Silguero, Ricardo (TUT) | 26
0
0
0
0
Groveland RNC Total |  | 26 | 1 | 5.2 | 74.29%
Kissimmee RNC
0
0
0
0
0
Kissimmee RNC Total |  | 0 | 0
Melbourne RNC
0
0
0
0
0
Melbourne RNC |  | 0 | 0
N Jacksonville RNC
| Y Brent Blair (TUT) | 5
0
0
0
0
N Jacksonville RNC Total |  | 5 | 1 | 1 | 14.29%
Ocala RNC
| Y Marshall, Dillan (TUT) | 12
0
0
0
0
Ocala RNC Total |  | 12 | 1 | 2.4 | 34.29%
Port St Lucie RNC
0
0
0
0
0
Port St Lucie RNC Total |  | 0 | 0
S Jacksonville RNC
| Y Baltazar, Abimael (TUT) | 18
0
0
0
0
S Jacksonville RNC Total |  | 18 | 1 | 3.6 | 51.43%
Sanford RNC
| Y Jose Santiago (TUT) | 11
| Y Jose Cruz (TUT) | 12
0
0
0
Sanford RNC Total |  | 23 | 2 | 2.3 | 32.86%
St Cloud RNC
| Y Jarvis, Michael (TUT) | 10
| Y Harf, Keith (TUT) | 3
0
0
0
St Cloud RNC Total |  | 13 | 2 | 1.3 | 18.57%
Tampa RNC
| Y Cordovi, Carlos (TUT) | 6
| Y Cruz, Jalierky (TUT) | 17
| Y Martin, Nick (TUT) | 4
0
0
Tampa RNC Total |  | 27 | 3 | 1.8 | 25.71%
Venice RNC
| Y Castaneda, Guadalupe (TUT) | 16
0
0
0
0
Venice RNC Total |  | 16 | 1 | 3.2 | 45.71%
Winter Garden RNC
| Y - Jackson, Amechi (TUT) | 17
0
0
0
0
Winter Garden RNC Total |  | 17 | 1 | 3.4 | 48.57%
Multi-Family
0
0
0
0
0
Multi-Family |  | 0 | 0
Grand Total |  | 271 | 22 | 2.4636 | 35.19%

## QA Report
[7 empty] | TUG | TUG | Phases | Target | 20 | LastRow | 148
[8 empty] | UG | Warranty
Count of Type Of Work |  |  |  |  | 5 | days in a week |  | T-Pole | QA
Office | QACrew | SQ-FT | Total | # active tuts | avg per Day | % To Target 20
Auburndale RNC
| Z Rivera, Corey (QA) | 21240 | 10
| Z Dickinson, Marvin (QA) | 11233 | 6
| Z Christian, Paul (QA) | 19293 | 9
| Z Maxson, Damien (QA) | 20116 | 10
| Z Owen, Kevin (QA) | 5800 | 3
0
0
0
0
0
Auburndale RNC Total | Total | 77682 | 38 | 5 | 1.52 | 38%
Brooksville RNC
| Z Leal, Wilmer (QA) | 5899 | 3
| Z Vega, Mike (QA) | 6876 | 3
0
0
0
0
0
0
0
Brooksville RNC Total | Total | 12775 | 6 | 2 | 0.6 | 15%
Daytona RNC
| Z Waggoner, Nathaniel (QA) | 7128 | 3
| Z Moussette, Frank (QA) | 23696 | 13
0
0
0
0
Daytona RNC Total | Total | 30824 | 16 | 2 | 1.6 | 40%
Ft Myers RNC
0
0
0
0
0
0
0
0
Ft Myers RNC | Total | 0 | 0 | 0
Groveland RNC
| Z Nunez, Julio (QA) | 51129 | 23
| Z Giraldo, David Andres (QA) | 16462 | 6
| Z Ibarra, Rigoberto (QA) | 12718 | 7
0
0
0
0
0
Groveland RNC Total | Total | 80309 | 36 | 3 | 2.4 | 60%
Kissimmee RNC
| Z Torres, David (QA) | 10508 | 3
| Z Camacho, Andre (QA) | 1960 | 1
| Z Curtis, Johnson (QA) | 15689 | 6
| Z Inderjit, Avinash (QA) | 51362 | 17
0
Kissimmee RNC Total | Total | 79519 | 27 | 4 | 1.35 | 33.75%
Melbourne RNC
| Z Dean, Art (QA) | 8435 | 4
| Z Baird, Chris (QA) | 2468 | 1
0
0
0
Melbourne RNC | Total | 10903 | 5 | 2 | 0.5 | 12.5%
N Jacksonville RNC
| Z Donald, Russ (QA) | 7736 | 4
| Z Corey, Blake (QA) | 23037 | 10
0
0
0
N Jacksonville RNC Total | Total | 30773 | 14 | 2 | 1.4 | 35%
Ocala RNC
| Z Scarberry, Dana (QA) | 4429 | 2
0
0
0
0
Ocala RNC Total | Total | 4429 | 2 | 1 | 0.4 | 10%
Port St Lucie RNC
| Z Clemmons, Marshannon (QA) | 3743 | 2
| Z Berkoben, Jason (QA) | 4029 | 2
0
0
0
Port St Lucie RNC Total | Total | 7772 | 4 | 2 | 0.4 | 10%
S Jacksonville RNC
| Z Welker, Daniel (QA) | 9602 | 4
| Z Page, Terry (QA) | 14697 | 8
0
0
0
S Jacksonville RNC Total | Total | 24299 | 12 | 2 | 1.2 | 30%
Sanford RNC
| Z Greene, Matthew (QA) | 14537 | 7
| Z Browning, Scott (QA) | 8789 | 3
| Z Morrill, Christopher (QA) | 7089 | 3
| Z Czerniawski, Joseph (QA) | 7902 | 3
| Z Curry, Darryl (QA) | 25622 | 12
0
0
0
0
0
0
0
Sanford RNC Total | Total | 63939 | 28 | 5 | 1.12 | 28%
St Cloud RNC
| Z Harris, James (QA) | 9820 | 5
| Z Rivera, Wylmer (QA) | 14143 | 7
| Z Santos, Juan (QA) | 41605 | 21
0
0
0
0
St Cloud RNC Total | Total | 65568 | 33 | 3 | 2.2 | 55%
Tampa RNC
| Z McCord, Michael (QA) | 15943 | 7
| Z Perez, Yanier (QA) | 8498 | 5
| Z Baboolal, Gayah (QA) | 12004 | 5
0
0
0
0
0
0
0
Tampa RNC Total | Total | 36445 | 17 | 3 | 1.1333 | 28.33%
Venice RNC
| z Stilwell, Jerrold (QA) | 5529 | 3
| Z Diehl, Peter (QA) | 8814 | 4
| Z Nichols, John (Butch) (QA) | 11879 | 6
0
0
0
0
0
Venice RNC Total | Total | 26222 | 13 | 3 | 0.86667 | 21.67%
Winter Garden RNC
| Z - Taveras, Marino (QA) | 18660 | 6
| Z Johnson, Paul (QA) | 16925 | 6
0
0
0
0
0
0
0
Winter Garden RNC Total | Total | 35585 | 12 | 2 | 1.2 | 30%
Multi-Family
| Z Ramdeen (QA) | 8052 | 4
| Z Casas, Mauricio (QA) | 7937 | 4
0
0
0
0
0
Multi-Family | Total | 15989 | 8 | 2 | 0.8 | 20%
Grand Total | Total | 603033 | 271 | 43 | 1.2605 | 31.51%

## Supervisor Rough QA
[7 empty] | TUG | TUG |  | Target | 20 | LastRow | 148
[5 empty] | Weeks |  |  | UG | Rough QA
Count of Type Of Work |  |  |  |  | 1 |  |  | T-Pole
Office | Rough_QA |  | Total | # active Supervisors | avg per week | % To Target 20
Auburndale RNC
| ZZ Ramirez, Frank Rough QA | 25405 | 14
| ZZ Adkins, Scott Rough QA | 12667 | 7
| ZZ Strickler, Alan Rough QA | 23171 | 12
0
0
0
0
0
0
0
Auburndale RNC Total | Total | 61243 | 33 | 3 | 11 | 55%
Brooksville RNC
| ZZ Concepcion, Gladdys ROUGH QA | 24623 | 11
| ZZ Hooker, Freddie ROUGH QA | 21789 | 11
| ZZ Murch, Robert ROUGH QA | 18595 | 9
0
0
0
0
0
0
Brooksville RNC Total | Total | 65007 | 31 | 3 | 10.3333 | 51.67%
Daytona RNC
| ZZ Dean, Phillip ROUGH QA | 12869 | 7
| ZZ Bowers, Zachary ROUGH QA | 10575 | 6
0
0
0
0
Daytona RNC Total | Total | 23444 | 13 | 2 | 6.5 | 32.5%
Ft Myers RNC
| ZZ Steyskal, Nathan Rough QA | 0 | 0
0
0
0
0
0
0
0
Ft Myers RNC | Total | 0 | 0 | 1 | 0 | 0%
Groveland RNC
| ZZ Aleman, Felix Rough QA | 4622 | 2
| ZZ Herrera, Alvaro Rough QA | 16820 | 8
| ZZ Thomas, Michael Rough QA | 2601 | 1
0
0
0
0
0
Groveland RNC Total | Total | 24043 | 11 | 3 | 3.6667 | 18.33%
Kissimmee RNC
| ZZ Guzman, Lisandro Rough QA | 37364 | 11
0
0
0
0
Kissimmee RNC Total | Total | 37364 | 11 | 1 | 11 | 55%
Melbourne RNC
| ZZ Long, Jordan (ROUGH QA) | 2040 | 1
| ZZ Rogers, Mike (ROUGH QA) | 1867 | 1
0
0
0
Melbourne RNC | Total | 3907 | 2 | 2 | 1 | 5%
N Jacksonville RNC
| ZZ Monk, Adam Rough QA | 8544 | 4
0
0
0
0
N Jacksonville RNC Total | Total | 8544 | 4 | 1 | 4 | 20%
Ocala RNC
| ZZ Boucher, James ROUGH QA | 16766 | 9
0
0
0
0
Ocala RNC Total | Total | 16766 | 9 | 1 | 9 | 45%
Port St Lucie RNC
| ZZ Perlmutter, Mark ROUGH QA | 5058 | 3
0
0
0
0
Port St Lucie RNC Total | Total | 5058 | 3 | 1 | 3 | 15%
S Jacksonville RNC
| ZZ Rose, Geno Rough QA | 16095 | 7
| ZZ Otis, Ditannon Rough QA | 21655 | 11
0
0
0
S Jacksonville RNC Total | Total | 37750 | 18 | 2 | 9 | 45%
Sanford RNC
| ZZ Baker, Chris ROUGH QA | 12476 | 5
| ZZ Bogue, Brandon ROUGH QA | 9387 | 6
| ZZ Continanzi, James ROUGH QA | 13905 | 5
| ZZ Meier, Jeremy Rough QA | 0 | 0
| ZZ Ron Krueger Rough QA | 3291 | 1
| ZZ Ronald Krueger (Rough QA) | 25828 | 9
0
0
0
0
0
0
Sanford RNC Total | Total | 64887 | 26 | 6 | 4.3333 | 21.67%
St Cloud RNC
| ZZ David De-Grasse Rough QA | 10718 | 6
| ZZ Liles, Isaac Rough QA | 5370 | 3
| ZZ Leon, Humberto Rough QA | 8493 | 4
| ZZ Leija, Diego Rough QA | 3905 | 2
0
0
0
St Cloud RNC Total | Total | 28486 | 15 | 4 | 3.75 | 18.75%
Tampa RNC
| ZZ Miguel Concepcion ROUGH QA | 7674 | 3
| ZZ Rodriguez, Eder ROUGH QA | 18573 | 9
0
0
0
0
0
0
0
0
Tampa RNC Total | Total | 26247 | 12 | 2 | 6 | 30%
Venice RNC
| ZZ Palmucci, James ROUGH QA | 14319 | 8
| ZZ Rodriguez, Pedro ROUGH QA | 10966 | 6
0
0
0
0
0
0
Venice RNC Total | Total | 25285 | 14 | 2 | 7 | 35%
Winter Garden RNC
| ZZ Alderman, Jody Rough QA | 12048 | 4
| ZZ Ellis, Berman Rough QA | 5646 | 2
0
0
0
0
0
0
0
Winter Garden RNC Total | Total | 17694 | 6 | 2 | 3 | 15%
Multi-Family
0
0
0
0
0
0
0
Multi-Family | Total | 0 | 0 | 0
Grand Total | Total | 445725 | 208 | 36 | 5.7778 | 28.89%

## Shop Productivity
|  |  | 1 weeks | 5 | 1207.3864
| Shop | Total Square ft. | crews | avg per crew | avg per day
1 | N Jacksonville RNC | 26166 | 7 | 3738 | 747.6 | 61.92%
2 | Brooksville RNC | 47628 | 12 | 3969 | 793.8 | 65.75%
3 | Winter garden RNC | 33199 | 7 | 4742.7143 | 948.5429 | 78.56%
4 | Ocala RNC | 25468 | 7 | 3638.2857 | 727.6571 | 60.27%
5 | S Jacksonville RNC | 70766 | 10 | 7076.6 | 1415.32 | 117.2%
6 | Groveland RNC | 39694 | 9 | 4410.4444 | 882.0889 | 73.06%
7 | Venice RNC | 36983 | 8 | 4622.875 | 924.575 | 76.58%
8 | Kissimmee RNC | 62990 | 13 | 4845.3846 | 969.0769 | 80.26%
9 | Tampa RNC | 57354 | 17 | 3373.7647 | 674.7529 | 55.89%
10 | St Cloud RNC | 56116 | 17 | 3300.9412 | 660.1882 | 54.68%
11 | Auburndale RNC | 72109 | 22 | 3277.6818 | 655.5364 | 54.29%
12 | Sanford RNC | 69115 | 15 | 4607.6667 | 921.5333 | 76.32%
13 | Daytona RNC | 33719 | 9 | 3746.5556 | 749.3111 | 62.06%
14 | Port St Lucie RNC | 17380 | 7 | 2482.8571 | 496.5714 | 41.13%
15 | Ft Myers RNC | 37550 | 7 | 5364.2857 | 1072.8571 | 88.86%
16 | Melbourne RNC | 28946 | 6 | 4824.3333 | 964.8667 | 79.91%
17 | Multi-Family | 3014 | 1 | 3014 | 602.8 | 49.93%