## Productivity
[7 empty] | Previous week Productivity | YTD Productivity new tab |  | Week | Days |  |  |  |  | LastRow | 316
[10 empty] | 1 weeks | 5
Count of Type Of Work | TOTAL | 227 | 556 | 289 | 537 | 233 | 263 | 288 | 1157717 | 231543.4 | 1230.5825
Office | Name | Rough QA | QA (Crew) | QA | TUT | Warranty | Rough | Trim | SQFT Production | SQFT per day | weight | SQFT to standard | Target | Emp 1st WO on this report | last WO on ytd report
S Jacksonville RNC | Larios Construction (Sub Labor) |  | 5 |  |  |  | 13 | 4 | 33401 | 6680.2 | 1000 | 5000 | 668% | 12/09/2019
Auburndale RNC | Camilo Ibar Services (sub Labor) |  | 5 |  |  |  | 13 |  | 24127 | 4825.4 | 1000 | 5000 | 482.5% | 12/09/2019
Ft Myers RNC | James Cogley LLC (FT Myers Sub) |  |  |  | 5 |  | 9 |  | 16801 | 3360.2 | 1000 | 5000 | 336% | 12/06/2019
Tampa RNC | Jjany - (Sub Labor) Group - Jimmy |  | 1 |  |  |  | 6 |  | 14052 | 2810.4 | 1000 | 5000 | 281% | 11/22/2019
Ft Myers RNC | Lucas Cirilo, Manuel |  | 2 |  | 5 |  | 6 |  | 10540 | 2108 | 1000 | 5000 | 210.8% | 12/06/2019
Venice RNC | Green Electric (Tampa) Sub Labor | [5 empty] | 6 |  | 10123 | 2024.6 | 1000 | 5000 | 202.5% | 12/05/2019
Auburndale RNC | Torres,Jesus | [6 empty] | 7 | 14836 | 2967.2 | 1500 | 7500 | 197.8% | 12/09/2019
Sanford RNC | BATC Sanford | [6 empty] | 7 | 14693 | 2938.6 | 1500 | 7500 | 195.9% | 12/06/2019
Sanford RNC | Steven's Maintenance (Sub Labor) | [5 empty] | 4 |  | 9682 | 1936.4 | 1000 | 5000 | 193.6% | 12/06/2019
Tampa RNC | Ramos, Jose |  | 4 |  |  |  | 5 |  | 9628 | 1925.6 | 1000 | 5000 | 192.6% | 12/11/2019
Sanford RNC | Nelms Dynasty (sub Labor) | [5 empty] | 3 |  | 9478 | 1895.6 | 1000 | 5000 | 189.6% | 11/07/2019
Sanford RNC | North Orlando Training Crew |  | 1 |  |  |  | 3 | 3 | 11188 | 2237.6 | 1250 | 6250 | 179% | 12/06/2019
S Jacksonville RNC | Jason Brady | [6 empty] | 6 | 13313 | 2662.6 | 1500 | 7500 | 177.5% | 12/12/2019
Brooksville RNC | West, Matthew |  | 5 |  |  |  | 2 |  | 8150 | 1630 | 1000 | 5000 | 163% | 12/10/2019
Sanford RNC | Kelly (Sub Labor) |  | 3 |  |  |  |  | 6 | 12114 | 2422.8 | 1500 | 7500 | 161.5% | 12/10/2019
Brooksville RNC | Concepcion, Moises |  | 1 |  |  |  |  | 6 | 11977 | 2395.4 | 1500 | 7500 | 159.7% | 12/07/2019
S Jacksonville RNC | Steven Kennedy |  | 1 |  |  |  |  | 4 | 11866 | 2373.2 | 1500 | 7500 | 158.2% | 12/05/2019
Venice RNC | Hanson, Travis | [6 empty] | 5 | 11850 | 2370 | 1500 | 7500 | 158% | 12/11/2019
Winter Garden RNC | Ponce, Jose |  | 1 |  |  |  |  | 5 | 11804 | 2360.8 | 1500 | 7500 | 157.4% | 12/12/2019
Kissimmee RNC | Elias |  | 1 |  |  |  | 2 |  | 7660 | 1532 | 1000 | 5000 | 153.2% | 12/05/2019
Tampa RNC | Gonzalez, Francisco | [5 empty] | 4 |  | 7511 | 1502.2 | 1000 | 5000 | 150.2% | 12/11/2019
Sanford RNC | Timothy Raymond | [6 empty] | 5 | 11008 | 2201.6 | 1500 | 7500 | 146.8% | 12/03/2019
S Jacksonville RNC | Alex Reyes | [6 empty] | 4 | 10966 | 2193.2 | 1500 | 7500 | 146.2% | 12/06/2019
Daytona RNC | Copeland |  |  |  | 8 |  |  | 7 | 10736 | 2147.2 | 1500 | 7500 | 143.1% | 12/09/2019
Groveland RNC | Cuba, Nerio |  | 1 | 1 |  |  |  | 5 | 10692 | 2138.4 | 1500 | 7500 | 142.6% | 12/09/2019
Auburndale RNC | Diaz, Yidiel | [6 empty] | 6 | 10502 | 2100.4 | 1500 | 7500 | 140% | 12/09/2019
Daytona RNC | Stevenson |  | 1 |  |  |  |  | 4 | 10483 | 2096.6 | 1500 | 7500 | 139.8% | 12/11/2019
St Cloud RNC | Vasquez Jose |  | 4 |  |  |  |  | 6 | 10466 | 2093.2 | 1500 | 7500 | 139.5% | 12/12/2019
S Jacksonville RNC | Daniel Wilkinson |  | 4 | 1 |  |  | 3 |  | 6971 | 1394.2 | 1000 | 5000 | 139.4% | 12/13/2019
Kissimmee RNC | Cesar, Dady | [5 empty] | 3 |  | 6865 | 1373 | 1000 | 5000 | 137.3% | 12/12/2019
Kissimmee RNC | Annulysse, Jean | [5 empty] | 3 |  | 6865 | 1373 | 1000 | 5000 | 137.3% | 12/12/2019
S Jacksonville RNC | Marshall Depreist (AP) |  | 3 |  |  |  |  | 6 | 10101 | 2020.2 | 1500 | 7500 | 134.7% | 12/09/2019
N Jacksonville RNC | Mcclough - Mcclough | [6 empty] | 5 | 10029 | 2005.8 | 1500 | 7500 | 133.7% | 12/12/2019
Auburndale RNC | Pace, Melvin | [6 empty] | 5 | 9898 | 1979.6 | 1500 | 7500 | 132% | 12/06/2019
Venice RNC | Cabrera, Ramon | [5 empty] | 3 |  | 6567 | 1313.4 | 1000 | 5000 | 131.3% | 12/10/2019
Brooksville RNC | Ruiz, Yamel | [6 empty] | 4 | 9839 | 1967.8 | 1500 | 7500 | 131.2% | 12/11/2019
Ocala RNC | Chris Barrett |  | 1 |  |  |  |  | 5 | 9836 | 1967.2 | 1500 | 7500 | 131.1% | 12/03/2019
Brooksville RNC | Diaz,Delia | [6 empty] | 5 | 9791 | 1958.2 | 1500 | 7500 | 130.5% | 12/06/2019
Tampa RNC | Delgado, Jose | [6 empty] | 4 | 9735 | 1947 | 1500 | 7500 | 129.8% | 12/10/2019
Auburndale RNC | Eodice, Cody | [5 empty] | 3 |  | 6394 | 1278.8 | 1000 | 5000 | 127.9% | 12/05/2019
Tampa RNC | Laura, Patrick | [6 empty] | 4 | 9436 | 1887.2 | 1500 | 7500 | 125.8% | 12/10/2019
Ocala RNC | Switzer, Justin | [6 empty] | 5 | 9411 | 1882.2 | 1500 | 7500 | 125.5% | 12/09/2019
Kissimmee RNC | AP John Nino Rivas |  | 1 |  |  |  | 2 | 1 | 7629 | 1525.8 | 1250 | 6250 | 122.1% | 12/12/2019
Ocala RNC | Roberto Munoz | [5 empty] | 3 |  | 6063 | 1212.6 | 1000 | 5000 | 121.3% | 12/11/2019
Kissimmee RNC | (AP) Jose Blanco |  | 1 |  |  |  | 1 | 2 | 7542 | 1508.4 | 1250 | 6250 | 120.7% | 12/12/2019
Tampa RNC | Williams, Charlie JR (Dad) |  | 2 |  |  |  | 2 |  | 6015 | 1203 | 1000 | 5000 | 120.3% | 12/09/2019
Brooksville RNC | Glenn,Jason | [5 empty] | 3 |  | 6012 | 1202.4 | 1000 | 5000 | 120.2% | 12/06/2019
Groveland RNC | Delgado, Jesus |  | 2 |  |  |  | 2 |  | 5937 | 1187.4 | 1000 | 5000 | 118.7% | 12/12/2019
Ocala RNC | Jules Etienne | [5 empty] | 3 |  | 5937 | 1187.4 | 1000 | 5000 | 118.7% | 12/10/2019
Melbourne RNC | Richey, Kyle |  | 5 |  |  |  |  | 4 | 8742 | 1748.4 | 1500 | 7500 | 116.6% | 12/09/2019
Sanford RNC | Silverstein | [5 empty] | 3 |  | 5827 | 1165.4 | 1000 | 5000 | 116.5% | 12/10/2019
St Cloud RNC | Leca Jonathan | [6 empty] | 5 | 8733 | 1746.6 | 1500 | 7500 | 116.4% | 12/11/2019
Venice RNC | Santana, Yunior |  |  |  | 2 |  | 3 |  | 5689 | 1137.8 | 1000 | 5000 | 113.8% | 12/09/2019
Venice RNC | Kendrick, Jereme |  |  |  | 3 |  | 3 |  | 5626 | 1125.2 | 1000 | 5000 | 112.5% | 12/04/2019
Port St Lucie RNC | Whyte | [5 empty] | 3 |  | 5545 | 1109 | 1000 | 5000 | 110.9% | 12/06/2019
N Jacksonville RNC | Travis Brown |  | 1 |  |  |  | 1 | 3 | 8257 | 1651.4 | 1500 | 7500 | 110.1% | 12/06/2019
Sanford RNC | AP Elswoth Busano | 1 | [5 empty] | 3 | 8121 | 1624.2 | 1500 | 7500 | 108.3% | 11/29/2019
Tampa RNC | Pipe, Anthony |  | 1 |  |  |  | 1 | 3 | 8029 | 1605.8 | 1500 | 7500 | 107.1% | 12/13/2019
Melbourne RNC | Soto, Nelson |  | 2 |  |  |  |  | 4 | 8009 | 1601.8 | 1500 | 7500 | 106.8% | 12/11/2019
N Jacksonville RNC | Boucher, Mathew Eugene |  | 3 |  |  |  | 2 |  | 5328 | 1065.6 | 1000 | 5000 | 106.6% | 12/12/2019
St Cloud RNC | Rojas, David |  | 3 |  |  |  | 3 |  | 5320 | 1064 | 1000 | 5000 | 106.4% | 12/11/2019
Tampa RNC | Moreira Gonzalez, Lixander |  | 1 |  |  |  |  | 4 | 7968 | 1593.6 | 1500 | 7500 | 106.2% | 12/11/2019
Sanford RNC | Fleming |  | 1 |  |  |  | 2 | 1 | 6596 | 1319.2 | 1250 | 6250 | 105.5% | 12/11/2019
Groveland RNC | Huggins, Gerardo |  | 1 |  |  |  |  | 3 | 7773 | 1554.6 | 1500 | 7500 | 103.6% | 12/13/2019
St Cloud RNC | Mollinedo, Darian |  | 1 |  |  |  | 3 |  | 5084 | 1016.8 | 1000 | 5000 | 101.7% | 12/10/2019
St Cloud RNC | Carranza Pierre | [5 empty] | 2 | 1 | 6344 | 1268.8 | 1250 | 6250 | 101.5% | 12/10/2019
Melbourne RNC | Sevcik, Eric |  |  | 1 |  |  | 3 |  | 5053 | 1010.6 | 1000 | 5000 | 101.1% | 12/05/2019
N Jacksonville RNC | Sergio Martinez |  | 1 |  |  |  | 2 |  | 4967 | 993.4 | 1000 | 5000 | 99.34% | 12/04/2019
Groveland RNC | Del Valle, Emanuel |  | 1 |  |  |  | 2 |  | 4961 | 992.2 | 1000 | 5000 | 99.22% | 12/06/2019
Brooksville RNC | James Cogley LLC (Sub Labor Brooksville) | [5 empty] | 3 |  | 4937 | 987.4 | 1000 | 5000 | 98.74% | 12/10/2019
S Jacksonville RNC | Nathan Hardy | [5 empty] | 3 |  | 4909 | 981.8 | 1000 | 5000 | 98.18% | 12/06/2019
S Jacksonville RNC | Darren Ferrell |  | 4 |  |  |  |  | 4 | 7201 | 1440.2 | 1500 | 7500 | 96.01% | 12/11/2019
Winter Garden RNC | Espanga, Derosema |  | 1 |  |  |  | 2 |  | 4800 | 960 | 1000 | 5000 | 96% | 12/06/2019
Auburndale RNC | Mercado, Alexander | [5 empty] | 1 | 2 | 5977 | 1195.4 | 1250 | 6250 | 95.63% | 12/06/2019
Brooksville RNC | Nevares, Jesus |  | 2 |  |  |  |  | 4 | 7150 | 1430 | 1500 | 7500 | 95.33% | 12/13/2019
Auburndale RNC | Keith, Nicholas | [5 empty] | 2 |  | 4760 | 952 | 1000 | 5000 | 95.2% | 12/11/2019
Sanford RNC | Spicer |  |  |  | 2 |  | 1 | 2 | 5944 | 1188.8 | 1250 | 6250 | 95.1% | 12/04/2019
Groveland RNC | Reynoso, Ramon |  | 1 |  |  |  | 2 |  | 4668 | 933.6 | 1000 | 5000 | 93.36% | 12/11/2019
Winter Garden RNC | Gutierrez, Sergio |  | 2 |  |  |  | 2 |  | 4613 | 922.6 | 1000 | 5000 | 92.26% | 12/13/2019
Tampa RNC | Alfonso, Jose | [6 empty] | 4 | 6891 | 1378.2 | 1500 | 7500 | 91.88% | 12/06/2019
Sanford RNC | Crespo | [5 empty] | 2 |  | 4585 | 917 | 1000 | 5000 | 91.7% | 12/09/2019
Groveland RNC | Stanzione, Giuseppe | [5 empty] | 2 |  | 4512 | 902.4 | 1000 | 5000 | 90.24% | 12/05/2019
Auburndale RNC | Francisco Torres | [5 empty] | 2 |  | 4489 | 897.8 | 1000 | 5000 | 89.78% | 12/05/2019
Sanford RNC | Anes, Roberto | [5 empty] | 1 | 1 | 5537 | 1107.4 | 1250 | 6250 | 88.59% | 12/09/2019
Sanford RNC | Edwards | [6 empty] | 2 | 6585 | 1317 | 1500 | 7500 | 87.8% | 12/06/2019
Tampa RNC | Ramirez,Marco |  | 2 |  |  |  | 2 |  | 4372 | 874.4 | 1000 | 5000 | 87.44% | 12/03/2019
Winter Garden RNC | Santiago, Edwin | [5 empty] | 2 |  | 4343 | 868.6 | 1000 | 5000 | 86.86% | 12/10/2019
Kissimmee RNC | Delaney Dennis |  | 2 |  |  |  | 1 |  | 4304 | 860.8 | 1000 | 5000 | 86.08% | 12/05/2019
Kissimmee RNC | Eric Harmon | [5 empty] | 2 |  | 4294 | 858.8 | 1000 | 5000 | 85.88% | 12/09/2019
Melbourne RNC | Webster, Garrett | [5 empty] | 2 |  | 4292 | 858.4 | 1000 | 5000 | 85.84% | 12/09/2019
Auburndale RNC | Rivera, Miguel | [6 empty] | 3 | 6431 | 1286.2 | 1500 | 7500 | 85.75% | 12/09/2019
Kissimmee RNC | Martinez, Marycarmen | [6 empty] | 2 | 6425 | 1285 | 1500 | 7500 | 85.67% | 12/09/2019
Multi-Family | 4954 Maintenance (Sub Labor) | [6 empty] | 2 | 6372 | 1274.4 | 1500 | 7500 | 84.96% | 12/06/2019
St Cloud RNC | Locorini, Jason | [5 empty] | 1 | 1 | 5308 | 1061.6 | 1250 | 6250 | 84.93% | 12/10/2019
Sanford RNC | Terrero |  | 1 |  |  |  | 1 | 1 | 5225 | 1045 | 1250 | 6250 | 83.6% | 12/10/2019
Sanford RNC | Bassett | [6 empty] | 3 | 6257 | 1251.4 | 1500 | 7500 | 83.43% | 12/09/2019
Auburndale RNC | Camilo Ibar (Mario) | [5 empty] | 2 |  | 4156 | 831.2 | 1000 | 5000 | 83.12% | 12/12/2019
Groveland RNC | Christie, Norman |  | 1 |  |  |  | 1 | 2 | 5114 | 1022.8 | 1250 | 6250 | 81.82% | 12/05/2019
Brooksville RNC | McElvain, Patrick |  | 2 |  |  |  | 1 | 1 | 5027 | 1005.4 | 1250 | 6250 | 80.43% | 12/06/2019
Brooksville RNC | Moats, Clint | [5 empty] | 2 |  | 4000 | 800 | 1000 | 5000 | 80% | 12/06/2019
St Cloud RNC | Jackson Trelon |  | 2 |  |  |  | 2 |  | 4000 | 800 | 1000 | 5000 | 80% | 12/06/2019
St Cloud RNC | Rojas, Axel |  | 1 |  |  |  | 2 | 1 | 4981 | 996.2 | 1250 | 6250 | 79.7% | 12/12/2019
Melbourne RNC | Fleming James |  | 5 |  |  |  |  | 3 | 5964 | 1192.8 | 1500 | 7500 | 79.52% | 12/13/2019
Daytona RNC | Connolly | [5 empty] | 2 |  | 3966 | 793.2 | 1000 | 5000 | 79.32% | 12/03/2019
N Jacksonville RNC | Aleksander Moroz |  | 1 |  |  |  | 2 |  | 3966 | 793.2 | 1000 | 5000 | 79.32% | 12/05/2019
Sanford RNC | Passwaters, Talen | [6 empty] | 3 | 5860 | 1172 | 1500 | 7500 | 78.13% | 12/04/2019
Daytona RNC | Carcano | [6 empty] | 3 | 5792 | 1158.4 | 1500 | 7500 | 77.23% | 12/12/2019
Ft Myers RNC | Montejo, Maria |  | 2 |  | 2 |  | 2 |  | 3850 | 770 | 1000 | 5000 | 77% | 12/04/2019
Brooksville RNC | Wienke, Adam | [5 empty] | 2 |  | 3847 | 769.4 | 1000 | 5000 | 76.94% | 12/09/2019
Kissimmee RNC | Vega, Antonio |  | 1 |  |  |  | 1 |  | 3802 | 760.4 | 1000 | 5000 | 76.04% | 12/05/2019
Auburndale RNC | Melendez, Juan | [5 empty] | 2 |  | 3777 | 755.4 | 1000 | 5000 | 75.54% | 12/04/2019
Tampa RNC | Boyd, Dave | [5 empty] | 2 |  | 3764 | 752.8 | 1000 | 5000 | 75.28% | 12/02/2019
Melbourne RNC | Oneal, Tracy |  | 2 |  |  |  | 2 |  | 3725 | 745 | 1000 | 5000 | 74.5% | 12/11/2019
Ft Myers RNC | Breese, Jonathan | [6 empty] | 3 | 5581 | 1116.2 | 1500 | 7500 | 74.41% | 12/05/2019
Auburndale RNC | Pedraza Gonzalez, Rafael | [6 empty] | 3 | 5578 | 1115.6 | 1500 | 7500 | 74.37% | 12/05/2019
Kissimmee RNC | Cruz, Kevin |  | 2 |  |  |  |  | 2 | 5517 | 1103.4 | 1500 | 7500 | 73.56% | 11/15/2019
Auburndale RNC | Mario Bargaineer | [5 empty] | 2 |  | 3671 | 734.2 | 1000 | 5000 | 73.42% | 12/11/2019
Brooksville RNC | Urbina,Jose | [5 empty] | 2 |  | 3656 | 731.2 | 1000 | 5000 | 73.12% | 12/09/2019
Groveland RNC | Perez, Edmundo | [5 empty] | 2 |  | 3648 | 729.6 | 1000 | 5000 | 72.96% | 12/06/2019
Groveland RNC | Quinones, Ray Jr |  | 1 |  |  |  | 2 |  | 3618 | 723.6 | 1000 | 5000 | 72.36% | 12/10/2019
Sanford RNC | Meahl Gregory | [6 empty] | 2 | 5408 | 1081.6 | 1500 | 7500 | 72.11% | 12/05/2019
Melbourne RNC | Gonzalez, Girardo |  | 2 |  |  |  | 2 |  | 3582 | 716.4 | 1000 | 5000 | 71.64% | 12/11/2019
N Jacksonville RNC | Alexander Pecherin | [6 empty] | 3 | 5345 | 1069 | 1500 | 7500 | 71.27% | 12/06/2019
Daytona RNC | Carter |  | 1 |  |  |  | 2 |  | 3548 | 709.6 | 1000 | 5000 | 70.96% | 12/09/2019
Daytona RNC | AP Stramondo | [5 empty] | 1 | 1 | 4278 | 855.6 | 1250 | 6250 | 68.45% | 12/11/2019
St Cloud RNC | South Orlando Training Crew |  | 2 |  |  |  | 2 |  | 3407 | 681.4 | 1000 | 5000 | 68.14% | 12/06/2019
Tampa RNC | Berice, Derius | [6 empty] | 2 | 5083 | 1016.6 | 1500 | 7500 | 67.77% | 12/12/2019
Auburndale RNC | Griffin, Nathan | [5 empty] | 2 |  | 3372 | 674.4 | 1000 | 5000 | 67.44% | 12/05/2019
Brooksville RNC | Huntoon, Edward |  | 4 |  |  |  | 2 |  | 3371 | 674.2 | 1000 | 5000 | 67.42% | 12/11/2019
Tampa RNC | Pineda, Noel | [6 empty] | 3 | 5039 | 1007.8 | 1500 | 7500 | 67.19% | 12/06/2019
Winter Garden RNC | Del Valle, David |  | 6 |  |  |  | 1 |  | 3328 | 665.6 | 1000 | 5000 | 66.56% | 12/11/2019
Auburndale RNC | Mojica,Eddie | [5 empty] | 2 |  | 3315 | 663 | 1000 | 5000 | 66.3% | 12/03/2019
Port St Lucie RNC | Sherba | [6 empty] | 3 | 4907 | 981.4 | 1500 | 7500 | 65.43% | 12/11/2019
S Jacksonville RNC | Kirk Thomer |  | 1 |  |  |  | 1 | 1 | 4058 | 811.6 | 1250 | 6250 | 64.93% | 12/09/2019
N Jacksonville RNC | Evan Wagner LLC | [5 empty] | 1 |  | 3231 | 646.2 | 1000 | 5000 | 64.62% | 12/02/2019
Auburndale RNC | Adkins,Charles | [6 empty] | 2 | 4844 | 968.8 | 1500 | 7500 | 64.59% | 12/09/2019
Winter Garden RNC | Cemeco, Luis |  | 2 |  |  |  | 2 |  | 3216 | 643.2 | 1000 | 5000 | 64.32% | 12/09/2019
Winter Garden RNC | Pirela, Carlos |  | 2 |  |  |  |  | 2 | 4805 | 961 | 1500 | 7500 | 64.07% | 12/11/2019
Ocala RNC | Steven Maculewics | [5 empty] | 2 |  | 3184 | 636.8 | 1000 | 5000 | 63.68% | 12/07/2019
Auburndale RNC | Luis Montada | [6 empty] | 3 | 4757 | 951.4 | 1500 | 7500 | 63.43% | 12/06/2019
Port St Lucie RNC | Wymer |  | 2 |  |  |  | 2 |  | 3169 | 633.8 | 1000 | 5000 | 63.38% | 12/12/2019
Venice RNC | Given,James Jr | [6 empty] | 2 | 4707 | 941.4 | 1500 | 7500 | 62.76% | 12/10/2019
Winter Garden RNC | Valverde, Armando |  | 1 |  |  |  |  | 2 | 4684 | 936.8 | 1500 | 7500 | 62.45% | 12/09/2019
Ocala RNC | Jonathan Lopez |  |  |  | 2 |  | 2 |  | 3088 | 617.6 | 1000 | 5000 | 61.76% | 12/03/2019
St Cloud RNC | Rivera Nelson | [6 empty] | 2 | 4448 | 889.6 | 1500 | 7500 | 59.31% | 12/10/2019
Winter Garden RNC | Rodriguez, Ronnie |  | 1 |  |  |  |  | 2 | 4400 | 880 | 1500 | 7500 | 58.67% | 12/10/2019
S Jacksonville RNC | Byers, Jerad |  | 7 |  |  |  |  | 2 | 4332 | 866.4 | 1500 | 7500 | 57.76% | 12/06/2019
Kissimmee RNC | Maldonado | [6 empty] | 1 | 4304 | 860.8 | 1500 | 7500 | 57.39% | 12/09/2019
Port St Lucie RNC | Johnston | [6 empty] | 2 | 4294 | 858.8 | 1500 | 7500 | 57.25% | 12/09/2019
Sanford RNC | Ramirez | [6 empty] | 2 | 4251 | 850.2 | 1500 | 7500 | 56.68% | 11/29/2019
Auburndale RNC | Vega, Ramon | [6 empty] | 2 | 4221 | 844.2 | 1500 | 7500 | 56.28% | 12/06/2019
St Cloud RNC | Morales, Walter | [5 empty] | 1 |  | 2809 | 561.8 | 1000 | 5000 | 56.18% | 12/05/2019
Venice RNC | Ponce, Adonis | [6 empty] | 2 | 4028 | 805.6 | 1500 | 7500 | 53.71% | 12/05/2019
Corporate | Tanner | [6 empty] | 2 | 3978 | 795.6 | 1500 | 7500 | 53.04% | 12/05/2019
Tampa RNC | Owens, Ron |  | 16 |  |  | 4 |  | 2 | 3966 | 793.2 | 1500 | 7500 | 52.88% | 12/13/2019
Daytona RNC | Rivera, Felix | [5 empty] | 1 | 1 | 3253 | 650.6 | 1250 | 6250 | 52.05% | 12/11/2019
Auburndale RNC | Hartley, Thomas | [5 empty] | 1 |  | 2599 | 519.8 | 1000 | 5000 | 51.98% | 12/09/2019
Venice RNC | Espinosa, Roy |  |  |  | 1 |  | 1 |  | 2581 | 516.2 | 1000 | 5000 | 51.62% | 12/05/2019
Winter Garden RNC | De Jesus, Pedro |  | 5 |  |  |  | 1 |  | 2500 | 500 | 1000 | 5000 | 50% | 12/10/2019
Winter Garden RNC | Rodriguez, Leonardo |  | 3 |  |  |  | 1 |  | 2500 | 500 | 1000 | 5000 | 50% | 12/12/2019
St Cloud RNC | Castaldi Joseph | [6 empty] | 2 | 3660 | 732 | 1500 | 7500 | 48.8% | 12/11/2019
Ft Myers RNC | Safford, Joe |  | 2 |  | 1 |  | 1 |  | 2431 | 486.2 | 1000 | 5000 | 48.62% | 12/10/2019
Kissimmee RNC | Aguayo, Antonio |  | 1 |  |  |  | 1 |  | 2334 | 466.8 | 1000 | 5000 | 46.68% | 12/11/2019
Sanford RNC | Brian Durval | [5 empty] | 2 |  | 2327 | 465.4 | 1000 | 5000 | 46.54% | 12/09/2019
Daytona RNC | Whited | [5 empty] | 1 |  | 2306 | 461.2 | 1000 | 5000 | 46.12% | 11/29/2019
Tampa RNC | Rodriguez, Emilio | [5 empty] | 1 |  | 2275 | 455 | 1000 | 5000 | 45.5% | 12/06/2019
Groveland RNC | Morocho, Danny |  | 1 |  |  |  | 1 |  | 2274 | 454.8 | 1000 | 5000 | 45.48% | 12/12/2019
Daytona RNC | Pierce_P | [5 empty] | 1 |  | 2262 | 452.4 | 1000 | 5000 | 45.24% | 12/06/2019
Tampa RNC | Gomez, Eulalio |  | 2 |  |  |  | 1 |  | 2233 | 446.6 | 1000 | 5000 | 44.66% | 12/05/2019
Port St Lucie RNC | Yepez |  | 1 |  |  |  |  | 2 | 3285 | 657 | 1500 | 7500 | 43.8% | 12/13/2019
Kissimmee RNC | (AP) Arroyo Burgos, Jose | [6 empty] | 1 | 3275 | 655 | 1500 | 7500 | 43.67% | 12/09/2019
S Jacksonville RNC | Smith | [6 empty] | 1 | 3146 | 629.2 | 1500 | 7500 | 41.95% | 11/27/2019
Daytona RNC | Seraphin Antoine | [5 empty] | 1 |  | 2045 | 409 | 1000 | 5000 | 40.9% | 12/09/2019
Brooksville RNC | ZZ Hooker, Freddie ROUGH QA | 11 | 18 |  |  |  |  | 1 | 3029 | 605.8 | 1500 | 7500 | 40.39% | 12/07/2019
St Cloud RNC | Sandoval Luis |  | 3 |  |  |  | 1 |  | 1989 | 397.8 | 1000 | 5000 | 39.78% | 12/11/2019
Tampa RNC | Bennett, Scott |  | 2 |  |  |  | 1 |  | 1969 | 393.8 | 1000 | 5000 | 39.38% | 12/10/2019
Brooksville RNC | Keys, Michael |  | 2 |  |  |  | 1 |  | 1966 | 393.2 | 1000 | 5000 | 39.32% | 12/06/2019
Sanford RNC | Austin, James |  |  |  | 5 |  | 1 |  | 1966 | 393.2 | 1000 | 5000 | 39.32% | 12/02/2019
Sanford RNC | Mitchell |  |  | 1 |  |  |  | 1 | 2916 | 583.2 | 1500 | 7500 | 38.88% | 11/15/2019
Daytona RNC | Kilpatrick | [5 empty] | 1 |  | 1915 | 383 | 1000 | 5000 | 38.3% | 12/06/2019
Brooksville RNC | Tirado, Omar | [5 empty] | 1 |  | 1861 | 372.2 | 1000 | 5000 | 37.22% | 12/06/2019
Ocala RNC | Devin Dickinson | [5 empty] | 1 |  | 1816 | 363.2 | 1000 | 5000 | 36.32% | 12/09/2019
Sanford RNC | AP William Pond |  | 1 |  |  |  |  | 1 | 2704 | 540.8 | 1500 | 7500 | 36.05% | 11/29/2019
Venice RNC | Cadet, Paul | [5 empty] | 1 |  | 1758 | 351.6 | 1000 | 5000 | 35.16% | 12/09/2019
Sanford RNC | Michael Lyng | [6 empty] | 1 | 2636 | 527.2 | 1500 | 7500 | 35.15% | 12/05/2019
Ft Myers RNC | Fabergas, Rolando | [6 empty] | 1 | 2609 | 521.8 | 1500 | 7500 | 34.79% | 12/05/2019
Kissimmee RNC | Francisco Campos | [6 empty] | 1 | 2599 | 519.8 | 1500 | 7500 | 34.65% | 12/11/2019
St Cloud RNC | Peterson, Rodrick | [6 empty] | 1 | 2535 | 507 | 1500 | 7500 | 33.8% | 12/06/2019
Brooksville RNC | Watts,Erik |  | 1 |  |  |  | 1 |  | 1673 | 334.6 | 1000 | 5000 | 33.46% | 12/11/2019
Brooksville RNC | Dwelly, Seth |  | 2 |  |  |  | 1 |  | 1673 | 334.6 | 1000 | 5000 | 33.46% | 12/10/2019
Brooksville RNC | Mcvey, Kyle | [5 empty] | 1 |  | 1673 | 334.6 | 1000 | 5000 | 33.46% | 12/04/2019
Venice RNC | Annicaro, Thomas | [5 empty] | 1 |  | 1673 | 334.6 | 1000 | 5000 | 33.46% | 12/06/2019
St Cloud RNC | Rivera Robert | [5 empty] | 1 |  | 1672 | 334.4 | 1000 | 5000 | 33.44% | 12/09/2019
Sanford RNC | Duxbury | [6 empty] | 1 | 2410 | 482 | 1500 | 7500 | 32.13% | 11/29/2019
Port St Lucie RNC | Buell |  | 1 |  |  |  | 1 |  | 1585 | 317 | 1000 | 5000 | 31.7% | 12/09/2019
Auburndale RNC | Wolf, David | [5 empty] | 1 |  | 1571 | 314.2 | 1000 | 5000 | 31.42% | 12/04/2019
Auburndale RNC | Acevedo, Jorge | [5 empty] | 1 |  | 1460 | 292 | 1000 | 5000 | 29.2% | 12/05/2019
Brooksville RNC | Marquez, Alexis |  | 1 |  |  |  |  | 1 | 2172 | 434.4 | 1500 | 7500 | 28.96% | 12/09/2019
Kissimmee RNC | Olivero, Moises Concepcion | [6 empty] | 1 | 2082 | 416.4 | 1500 | 7500 | 27.76% | 12/12/2019
Winter Garden RNC | Algarin, Joel |  | 5 |  |  |  |  | 1 | 2034 | 406.8 | 1500 | 7500 | 27.12% | 12/05/2019
Auburndale RNC | Tampa Training Crew | [6 empty] | 1 | 2032 | 406.4 | 1500 | 7500 | 27.09% | 12/05/2019
Ft Myers RNC | Allen, Sean |  | 2 |  |  |  |  | 1 | 2030 | 406 | 1500 | 7500 | 27.07% | 12/05/2019
St Cloud RNC | Chicoye Sadrak | [6 empty] | 1 | 1989 | 397.8 | 1500 | 7500 | 26.52% | 12/05/2019
Sanford RNC | AP Suheidy Vega Torres | [6 empty] | 1 | 1828 | 365.6 | 1500 | 7500 | 24.37% | 12/05/2019
Venice RNC | Sprague, Alec |  | 1 |  | 8 |  |  | 1 | 1702 | 340.4 | 1500 | 7500 | 22.69% | 12/11/2019
Sanford RNC | ZZ Bogue, Brandon ROUGH QA | 7 |  |  | 5 |  |  | 1 | 1614 | 322.8 | 1500 | 7500 | 21.52% | 12/06/2019
Auburndale RNC | ZZ Ramirez, Frank Rough QA | 12 | [11 empty] | 12/09/2019
Auburndale RNC | Z Rivera, Corey (QA) |  | 24 | 7 | [9 empty] | 12/13/2019
Auburndale RNC | Y Blue, Ricky (TUT) |  | 7 |  | 6 | [8 empty] | 12/10/2019
Auburndale RNC | ZZ Adkins, Scott Rough QA | 5 | [11 empty] | 12/11/2019
Auburndale RNC | Z Dickinson, Marvin (QA) |  | 1 |  |  | 16 | [7 empty] | 12/09/2019
Auburndale RNC | ZZ Strickler, Alan Rough QA | 8 | [11 empty] | 12/12/2019
Auburndale RNC | Z Christian, Paul (QA) |  | 2 | 9 | [9 empty] | 12/11/2019
Auburndale RNC | Z Maxson, Damien (QA) |  | 8 | 9 | [9 empty] | 12/10/2019
Auburndale RNC | Z Owen, Kevin (QA) |  | 1 |  |  | 13 | [7 empty] | 12/09/2019
Auburndale RNC | Y Beoto, Juan (TUT) |  |  |  | 18 | [8 empty] | 12/10/2019
Auburndale RNC | Y Morales, Jose (TUT) |  | 3 |  | 43 | [8 empty] | 12/11/2019
Brooksville RNC | ZZ Concepcion, Gladdys ROUGH QA | 8 |  |  |  | 1 | [7 empty] | 12/09/2019
Brooksville RNC | Z Leal, Wilmer (QA) |  | 2 | 12 |  | 2 | [7 empty] | 12/10/2019
Brooksville RNC | Y Gonzalez, Joan (TUT) |  | 7 |  | 23 | [8 empty] | 12/13/2019
Brooksville RNC | ZZ Murch, Robert ROUGH QA | 4 | [11 empty] | 12/09/2019
Brooksville RNC | Z Vega, Mike (QA) |  | 6 | 4 |  | 6 | [7 empty] | 12/10/2019
Brooksville RNC | Z Jutte, Thomas (QA) |  | 6 | 4 |  | 3 | [7 empty] | 12/12/2019
Brooksville RNC | Y Fortner, Russell (TUT) |  | 15 |  | 30 | [8 empty] | 12/09/2019
Brooksville RNC | Y Whiting, Michael (TUT) |  | 2 |  | 9 | [8 empty] | 12/12/2019
Daytona RNC | ZZ Dean, Phillip ROUGH QA | 6 | [11 empty] | 12/09/2019
Daytona RNC | ZZ Bowers, Zachary ROUGH QA | 3 | 2 | [10 empty] | 12/09/2019
Daytona RNC | Z Waggoner, Nathaniel (QA) |  | 10 | 5 | [9 empty] | 11/20/2019
Daytona RNC | Consalo |  | 1 | [10 empty] | 12/12/2019
Daytona RNC | Y DeWitt, Brett (TUT) |  | 7 |  | 7 | [8 empty] | 12/10/2019
Daytona RNC | Y Whitaker, Christopher (TUT) |  | 1 |  | 10 | [8 empty] | 12/13/2019
Daytona RNC | Z Moussette, Frank (QA) |  | 11 | 8 |  | 4 | [7 empty] | 12/13/2019
Ft Myers RNC | Z Duran, Eudy (QA) | 4 |  | 2 |  | 4 | [7 empty] | 12/10/2019
Ft Myers RNC | ZZ Steyskal, Nathan Rough QA | 2 | 2 | 10 |  | 3 | [7 empty] | 12/12/2019
Ft Myers RNC | Y Wade, Antonio (TUT) |  | 1 |  | 10 | [8 empty] | 12/04/2019
Groveland RNC | ZZ Aleman, Felix Rough QA | 3 | [11 empty] | 12/09/2019
Groveland RNC | Z Nunez, Julio (QA) |  | 3 | 10 |  | 2 | [7 empty] | 12/09/2019
Groveland RNC | Y Silguero, Ricardo (TUT) |  |  |  | 32 | [8 empty] | 12/10/2019
Groveland RNC | ZZ Herrera, Alvaro Rough QA | 11 | [11 empty] | 12/13/2019
Groveland RNC | Z Giraldo, David Andres (QA) |  | 6 | 5 |  | 3 | [7 empty] | 12/12/2019
Groveland RNC | ZZ Thomas, Michael Rough QA | 2 |  | 1 | [9 empty] | 12/11/2019
Groveland RNC | Z Ibarra, Rigoberto (QA) |  | 7 | 2 |  | 2 | [7 empty] | 12/12/2019
Kissimmee RNC | Z Torres, David (QA) |  | 1 | 4 | [9 empty] | 12/03/2019
Kissimmee RNC | ZZ Pereira, Decio Rough QA | 1 | [11 empty] | 12/09/2019
Kissimmee RNC | ZZ Camacho, Andre Rough QA | 1 | [11 empty] | 12/10/2019
Kissimmee RNC | ZZ Guzman, Lisandro Rough QA | 4 | [11 empty] | 12/09/2019
Kissimmee RNC | Z Curtis, Johnson (QA) |  |  |  |  | 18 | [7 empty] | 12/13/2019
Kissimmee RNC | Z Inderjit, Avinash (QA) |  |  | 3 | [9 empty] | 12/06/2019
Kissimmee RNC | Y Cruz Aquino, Bernardo (TUT) |  |  |  | 1 | [8 empty] | 12/13/2019
Kissimmee RNC | Y Cruz Andricain, Julio C (TUT) |  |  |  | 40 | [8 empty] | 11/22/2019
Kissimmee RNC | Guzman, Jonathan |  | 1 | [10 empty] | 12/10/2019
Kissimmee RNC | Francisco Reccy De Leon |  | 1 | [10 empty] | 12/10/2019
Melbourne RNC | ZZ Long, Jordan (ROUGH QA) | 7 | 1 | 6 | [9 empty] | 12/10/2019
Melbourne RNC | Z Dean, Art (QA) | 1 | 8 |  |  | 3 | [7 empty] | 12/13/2019
Melbourne RNC | Z Baird, Chris (QA) |  | 3 | 3 | 2 | [8 empty] | 12/10/2019
Melbourne RNC | ZZ Rogers, Mike (ROUGH QA) | 1 |  |  |  | 2 | [7 empty] | 12/11/2019
Multi-Family | Doug Thompson UG (Sub Labor) |  |  |  | 1 | [8 empty] | 12/11/2019
Multi-Family | ZZ Dallos, Francisco Rough QA | 1 |  | 1 | [9 empty] | 12/03/2019
Multi-Family | Z Ramdeen (QA) |  |  | 9 |  | 2 | [7 empty] | 12/10/2019
Multi-Family | ZZ Stratton, Stan Rough QA |  |  | 5 | [9 empty] | 12/05/2019
Multi-Family | Z Casas, Mauricio (QA) |  |  | 3 |  | 3 | [7 empty] | 12/10/2019
Multi-Family | Randy Silguero |  |  |  | 18 | [8 empty] | 09/30/2019
Multi-Family | Kelvin Febus Centeno |  |  |  | 1 | [8 empty] | 12/09/2019
Multi-Family | Jose Luis Medina Corzo |  |  |  | 1 | [8 empty] | 12/09/2019
Multi-Family | Z Garavito, Guillermo (QA) | [12 empty] | 12/06/2019
N Jacksonville RNC | Z Donald, Russ (QA) |  | 8 | 7 | [9 empty] | 12/10/2019
N Jacksonville RNC | Y Brent Blair (TUT) |  | 23 |  | 15 | 1 | [7 empty] | 12/13/2019
N Jacksonville RNC | ZZ Monk, Adam Rough QA | 8 | [11 empty] | 12/11/2019
N Jacksonville RNC | Z Corey, Blake (QA) |  | 15 | 3 |  | 10 | [7 empty] | 12/13/2019
Ocala RNC | Carl (Temp) |  |  |  | 2 | [8 empty] | 12/10/2019
Ocala RNC | ZZ Boucher, James ROUGH QA | 7 | 1 |  | 1 | [8 empty] | 12/10/2019
Ocala RNC | Z Scarberry, Dana (QA) |  | 5 | 9 |  | 2 | [7 empty] | 12/09/2019
Ocala RNC | Y Marshall, Dillan (TUT) |  |  |  | 20 | [8 empty] | 12/11/2019
Port St Lucie RNC | Z Clemmons, Marshannon (QA) |  | 15 | 4 | 7 | 11 | [7 empty] | 12/10/2019
Port St Lucie RNC | ZZ Perlmutter, Mark ROUGH QA | 6 | 1 | [10 empty] | 12/11/2019
Port St Lucie RNC | Mitchell Munroe |  | 1 | [10 empty] | 12/10/2019
Port St Lucie RNC | Z Berkoben, Jason (QA) | 5 | 6 |  |  | 2 | [7 empty] | 12/12/2019
S Jacksonville RNC | Z Welker, Daniel (QA) | 3 | 10 | 15 |  | 2 | [7 empty] | 12/13/2019
S Jacksonville RNC | ZZ Rose, Geno Rough QA | 13 | [11 empty] | 12/11/2019
S Jacksonville RNC | ZZ Otis, Ditannon Rough QA | 7 | 1 | [10 empty] | 12/11/2019
S Jacksonville RNC | Z Page, Terry (QA) |  | 1 | 3 |  | 6 | [7 empty] | 12/10/2019
S Jacksonville RNC | Y Baltazar, Abimael (TUT) |  | 10 |  | 21 | [8 empty] | 12/11/2019
Sanford RNC | Z Greene, Matthew (QA) |  | 3 | 7 |  | 7 | [7 empty] | 12/13/2019
Sanford RNC | Z Browning, Scott (QA) |  |  | 8 |  | 6 | [7 empty] | 12/11/2019
Sanford RNC | Z Morrill, Christopher (QA) |  |  | 11 | 3 | 6 | [7 empty] | 12/13/2019
Sanford RNC | Z Czerniawski, Joseph (QA) |  |  | 2 |  | 14 | [7 empty] | 12/11/2019
Sanford RNC | ZZ Baker, Chris ROUGH QA | 4 |  |  | 1 | [8 empty] | 12/11/2019
Sanford RNC | ZZ Continanzi, James ROUGH QA |  |  | 1 |  | 1 | [7 empty] | 12/11/2019
Sanford RNC | ZZ Meier, Jeremy Rough QA | 2 |  | 2 |  | 2 | [7 empty] | 12/11/2019
Sanford RNC | Y Jose Santiago (TUT) |  |  |  | 18 | [8 empty] | 12/06/2019
Sanford RNC | Z Curry, Darryl (QA) |  |  | 13 |  | 5 | [7 empty] | 12/06/2019
Sanford RNC | ZZ Ron Krueger Rough QA | 5 | [11 empty] | 12/12/2019
Sanford RNC | Y Jose Cruz (TUT) |  |  |  | 22 | [8 empty] | 12/06/2019
Service ORL | JAX - Luis Quero | [12 empty] | 12/11/2019
Service TPA | Al, Chiarelli | [12 empty] | 12/10/2019
Service TPA | Michael, Carrigan | [12 empty] | 12/13/2019
Service TPA | Yasmany, Gonzalez | [12 empty] | 12/09/2019
Service TPA | Billy, Brisson | [12 empty] | 12/11/2019
Service TPA | Hilario, Garcia | [12 empty] | 12/12/2019
St Cloud RNC | Y Jarvis, Michael (TUT) |  |  |  | 14 | [8 empty] | 12/04/2019
St Cloud RNC | Z Harris, James (QA) |  |  | 5 |  | 13 | [7 empty] | 12/10/2019
St Cloud RNC | Y Harf, Keith (TUT) |  |  |  | 11 | [8 empty] | 12/11/2019
St Cloud RNC | Z Rivera, Wylmer (QA) |  |  | 8 |  | 2 | [7 empty] | 12/13/2019
St Cloud RNC | ZZ Liles, Isaac Rough QA | 1 | [11 empty] | 12/10/2019
St Cloud RNC | ZZ Leon, Humberto Rough QA | 9 |  |  |  | 1 | [7 empty] | 12/13/2019
St Cloud RNC | ZZ Leija, Diego Rough QA | 3 | [11 empty] | 09/10/2019
St Cloud RNC | Z Santos, Juan (QA) |  |  | 16 |  | 6 | [7 empty] | 12/13/2019
St Cloud RNC | Z Basdeo Juman |  |  | 1 | [9 empty] | 11/20/2019
Tampa RNC | Y Cordovi, Carlos (TUT) |  | 4 |  | 26 | [8 empty] | 12/09/2019
Tampa RNC | Z McCord, Michael (QA) |  | 7 | 6 |  | 9 | [7 empty] | 12/10/2019
Tampa RNC | Y Cruz, Jalierky (TUT) |  |  |  | 16 | [8 empty] | 12/09/2019
Tampa RNC | Z Perez, Yanier (QA) |  |  | 4 |  | 3 | [7 empty] | 12/11/2019
Tampa RNC | ZZ Miguel Concepcion ROUGH QA | 12 | 2 | [10 empty] | 12/10/2019
Tampa RNC | ZZ Rodriguez, Eder ROUGH QA | 4 | [11 empty] | 12/12/2019
Tampa RNC | ZZ Severe, Anthony ROUGH QA | 1 |  |  |  | 1 | [7 empty] | 12/10/2019
Tampa RNC | Z Baboolal, Gayah (QA) |  | 13 | 6 |  | 6 | [7 empty] | 12/10/2019
Tampa RNC | Y Martin, Nick (TUT) |  | 6 |  | 9 | [8 empty] | 12/09/2019
Tampa RNC | JJANY (Brooksville) Sub Labor |  | 1 | [10 empty] | 12/09/2019
Tampa RNC | Green Electric (Brooksville) Sub Labor |  | 4 | [10 empty] | 12/04/2019
Venice RNC | z Stilwell, Jerrold (QA) |  | 13 | 6 | 5 | 1 | [7 empty] | 12/11/2019
Venice RNC | Y Castaneda, Guadalupe (TUT) |  |  |  | 27 | [8 empty] | 12/12/2019
Venice RNC | Z Diehl, Peter (QA) |  | 3 | 3 |  | 1 | [7 empty] | 12/11/2019
Venice RNC | ZZ Palmucci, James ROUGH QA | 6 | [11 empty] | 12/09/2019
Venice RNC | ZZ Rodriguez, Pedro ROUGH QA | 17 | [11 empty] | 12/11/2019
Venice RNC | ZZ Shannon Chafens Rough QA |  |  | 10 | [9 empty] | 12/10/2019
Venice RNC | Z Nichols, John (Butch) (QA) |  | 7 | 2 |  | 2 | [7 empty] | 12/12/2019
Winter Garden RNC | Z Jeantilhomme, Charite (QA) |  | 4 | 7 |  | 9 | [7 empty] | 12/09/2019
Winter Garden RNC | Z - Taveras, Marino (QA) |  | 23 | 3 |  | 3 | [7 empty] | 12/10/2019
Winter Garden RNC | Aponte, Felipe |  | 3 | [10 empty] | 12/09/2019
Winter Garden RNC | ZZ Alderman, Jody Rough QA | 5 | [11 empty] | 12/13/2019
Winter Garden RNC | ZZ Robles, Jared Rough QA | 2 | [11 empty] | 12/10/2019
Winter Garden RNC | ZZ Ellis, Berman Rough QA | 4 | 1 | [10 empty] | 12/11/2019
Winter Garden RNC | Y - Jackson, Amechi (TUT) |  | 8 |  | 18 | [8 empty] | 12/12/2019
Winter Garden RNC | Z Johnson, Paul (QA) |  |  | 1 |  | 10 | [7 empty] | 12/11/2019

## TUT Report
[6 empty] | TUG | TUG | LastRow | 83
UG
Count of Type Of Work |  |  | 3 |  |  |  | T-Pole
Office | Crew | Total | # active tuts | avg per Day | % To Target 35
Auburndale RNC
| Y Blue, Ricky (TUT) | 6
| Y Beoto, Juan (TUT) | 18
| Y Morales, Jose (TUT) | 43
0
0
Auburndale RNC Total |  | 67 | 3 | 4.4667 | 63.81%
Brooksville RNC
| Y Gonzalez, Joan (TUT) | 23
| Y Fortner, Russell (TUT) | 30
| Y Whiting, Michael (TUT) | 9
0
0
Brooksville RNC Total |  | 62 | 3 | 4.1333 | 59.05%
Daytona RNC
| Y DeWitt, Brett (TUT) | 7
| Y Whitaker, Christopher (TUT) | 10
0
0
0
Daytona RNC Total |  | 17 | 2 | 1.7 | 24.29%
FT Myers RNC
| Y Cruz Andricain, Julio C (TUT) | 0
0
0
0
0
FT Myers RNC |  | 0 | 1 | 0 | 0%
Groveland RNC
| Y Silguero, Ricardo (TUT) | 32
0
0
0
0
Groveland RNC Total |  | 32 | 1 | 6.4 | 91.43%
Kissimmee RNC
| Y Cruz Aquino, Bernardo (TUT) | 1
| Y Cruz Andricain, Julio C (TUT) | 40
0
0
0
Kissimmee RNC Total |  | 41 | 2 | 4.1 | 58.57%
Melbourne RNC
0
0
0
0
0
Melbourne RNC |  | 0 | 0
N Jacksonville RNC
| Y Brent Blair (TUT) | 15
0
0
0
0
N Jacksonville RNC Total |  | 15 | 1 | 3 | 42.86%
Ocala RNC
| Y Marshall, Dillan (TUT) | 20
0
0
0
0
Ocala RNC Total |  | 20 | 1 | 4 | 57.14%
Port St Lucie RNC
0
0
0
0
0
Port St Lucie RNC Total |  | 0 | 0
S Jacksonville RNC
| Y Baltazar, Abimael (TUT) | 21
0
0
0
0
S Jacksonville RNC Total |  | 21 | 1 | 4.2 | 60%
Sanford RNC
| Y Jose Santiago (TUT) | 18
| Y Jose Cruz (TUT) | 22
0
0
0
Sanford RNC Total |  | 40 | 2 | 4 | 57.14%
St Cloud RNC
| Y Jarvis, Michael (TUT) | 14
| Y Harf, Keith (TUT) | 11
0
0
0
St Cloud RNC Total |  | 25 | 2 | 2.5 | 35.71%
Tampa RNC
| Y Gonzalez, Joan (TUT) | 3
| Y Cordovi, Carlos (TUT) | 26
| Y Cruz, Jalierky (TUT) | 16
| Y Martin, Nick (TUT) | 9
0
Tampa RNC Total |  | 54 | 4 | 2.7 | 38.57%
Venice RNC
| Y Castaneda, Guadalupe (TUT) | 27
0
0
0
0
Venice RNC Total |  | 27 | 1 | 5.4 | 77.14%
Winter Garden RNC
| Y - Jackson, Amechi (TUT) | 18
0
0
0
0
Winter Garden RNC Total |  | 18 | 1 | 3.6 | 51.43%
Multi-Family
0
0
0
0
0
Multi-Family |  | 0 | 0
Grand Total |  | 439 | 25 | 3.512 | 50.17%

## QA Report
[7 empty] | TUG | TUG | Phases | Target | 20 | LastRow | 148
[8 empty] | UG | Warranty
Count of Type Of Work |  |  |  |  | 5 | days in a week |  | T-Pole | QA
Office | QACrew | SQ-FT | Total | # active tuts | avg per Day | % To Target 20
Auburndale RNC
| Z Rivera, Corey (QA) | 15113 | 7
| Z Dickinson, Marvin (QA) | 34316 | 16
| Z Christian, Paul (QA) | 20030 | 9
| Z Maxson, Damien (QA) | 17431 | 9
| Z Owen, Kevin (QA) | 27246 | 13
0
0
0
0
0
Auburndale RNC Total | Total | 114136 | 54 | 5 | 2.16 | 54%
Brooksville RNC
| Z Leal, Wilmer (QA) | 30252 | 14
| Z Vega, Mike (QA) | 24295 | 10
| Z Jutte, Thomas (QA) | 17201 | 7
0
0
0
0
0
0
Brooksville RNC Total | Total | 71748 | 31 | 3 | 2.0667 | 51.67%
Daytona RNC
| Z Waggoner, Nathaniel (QA) | 10823 | 5
| Z Moussette, Frank (QA) | 21756 | 12
0
0
0
0
Daytona RNC Total | Total | 32579 | 17 | 2 | 1.7 | 42.5%
Ft Myers RNC
| Z Duran, Eudy (QA) | 11751 | 6
0
0
0
0
0
0
0
Ft Myers RNC | Total | 11751 | 6 | 1 | 1.2 | 30%
Groveland RNC
| Z Nunez, Julio (QA) | 23201 | 12
| Z Giraldo, David Andres (QA) | 22307 | 8
| Z Ibarra, Rigoberto (QA) | 7576 | 4
0
0
0
0
0
Groveland RNC Total | Total | 53084 | 24 | 3 | 1.6 | 40%
Kissimmee RNC
| Z Torres, David (QA) | 14676 | 4
| Z Curtis, Johnson (QA) | 43595 | 18
| Z Inderjit, Avinash (QA) | 7807 | 3
| Z Garavito, Guillermo (QA) | 13746 | 6
0
Kissimmee RNC Total | Total | 79824 | 31 | 4 | 1.55 | 38.75%
Melbourne RNC
| Z Dean, Art (QA) | 6750 | 3
| Z Baird, Chris (QA) | 6121 | 3
0
0
0
Melbourne RNC | Total | 12871 | 6 | 2 | 0.6 | 15%
N Jacksonville RNC
| Z Donald, Russ (QA) | 13121 | 7
| Z Corey, Blake (QA) | 33070 | 13
0
0
0
N Jacksonville RNC Total | Total | 46191 | 20 | 2 | 2 | 50%
Ocala RNC
| Z Scarberry, Dana (QA) | 23241 | 11
0
0
0
0
Ocala RNC Total | Total | 23241 | 11 | 1 | 2.2 | 55%
Port St Lucie RNC
| Z Clemmons, Marshannon (QA) | 31754 | 15
| Z Berkoben, Jason (QA) | 5192 | 2
0
0
0
Port St Lucie RNC Total | Total | 36946 | 17 | 2 | 1.7 | 42.5%
S Jacksonville RNC
| Z Welker, Daniel (QA) | 31911 | 17
| Z Page, Terry (QA) | 22745 | 9
0
0
0
S Jacksonville RNC Total | Total | 54656 | 26 | 2 | 2.6 | 65%
Sanford RNC
| Z Greene, Matthew (QA) | 31640 | 14
| Z Browning, Scott (QA) | 36200 | 14
| Z Morrill, Christopher (QA) | 37310 | 17
| Z Czerniawski, Joseph (QA) | 44012 | 16
| Z Curry, Darryl (QA) | 37376 | 18
0
0
0
0
0
0
0
Sanford RNC Total | Total | 186538 | 79 | 5 | 3.16 | 79%
St Cloud RNC
| Z Harris, James (QA) | 38531 | 18
| Z Rivera, Wylmer (QA) | 18544 | 10
| Z Santos, Juan (QA) | 45676 | 22
0
0
0
0
St Cloud RNC Total | Total | 102751 | 50 | 3 | 3.3333 | 83.33%
Tampa RNC
| Z McCord, Michael (QA) | 35350 | 15
| Z Perez, Yanier (QA) | 13150 | 7
| Z Baboolal, Gayah (QA) | 29583 | 12
0
0
0
0
0
0
0
Tampa RNC Total | Total | 78083 | 34 | 3 | 2.2667 | 56.67%
Venice RNC
| z Stilwell, Jerrold (QA) | 16612 | 7
| Z Diehl, Peter (QA) | 7389 | 4
| Z Nichols, John (Butch) (QA) | 8478 | 4
0
0
0
0
0
Venice RNC Total | Total | 32479 | 15 | 3 | 1 | 25%
Winter Garden RNC
| Z Jeantilhomme, Charite (QA) | 49282 | 16
| Z - Taveras, Marino (QA) | 15427 | 6
| Z Johnson, Paul (QA) | 25430 | 11
0
0
0
0
0
0
Winter Garden RNC Total | Total | 90139 | 33 | 3 | 2.2 | 55%
Multi-Family
| Z Ramdeen (QA) | 19151 | 11
| Z Casas, Mauricio (QA) | 11478 | 6
0
0
0
0
0
Multi-Family | Total | 30629 | 17 | 2 | 1.7 | 42.5%
Grand Total | Total | 1057646 | 471 | 46 | 2.0478 | 51.2%

## Supervisor Rough QA
[7 empty] | TUG | TUG |  | Target | 20 | LastRow | 148
[5 empty] | Weeks |  |  | UG | Rough QA
Count of Type Of Work |  |  |  |  | 1 |  |  | T-Pole
Office | Rough_QA |  | Total | # active Supervisors | avg per week | % To Target 20
Auburndale RNC
| ZZ Ramirez, Frank Rough QA | 22820 | 12
| ZZ Adkins, Scott Rough QA | 9691 | 5
| ZZ Strickler, Alan Rough QA | 15431 | 8
0
0
0
0
0
0
0
Auburndale RNC Total | Total | 47942 | 25 | 3 | 8.3333 | 41.67%
Brooksville RNC
| ZZ Concepcion, Gladdys ROUGH QA | 20631 | 8
| ZZ Hooker, Freddie ROUGH QA | 19788 | 11
| ZZ Murch, Robert ROUGH QA | 9572 | 4
0
0
0
0
0
0
Brooksville RNC Total | Total | 49991 | 23 | 3 | 7.6667 | 38.33%
Daytona RNC
| ZZ Dean, Phillip ROUGH QA | 13455 | 6
| ZZ Bowers, Zachary ROUGH QA | 6092 | 3
0
0
0
0
Daytona RNC Total | Total | 19547 | 9 | 2 | 4.5 | 22.5%
Ft Myers RNC
| ZZ Steyskal, Nathan Rough QA | 3408 | 2
0
0
0
0
0
0
0
Ft Myers RNC | Total | 3408 | 2 | 1 | 2 | 10%
Groveland RNC
| ZZ Aleman, Felix Rough QA | 7408 | 3
| ZZ Herrera, Alvaro Rough QA | 23676 | 11
| ZZ Thomas, Michael Rough QA | 4748 | 2
0
0
0
0
0
Groveland RNC Total | Total | 35832 | 16 | 3 | 5.3333 | 26.67%
Kissimmee RNC
| ZZ Pereira, Decio Rough QA | 2109 | 1
| ZZ Camacho, Andre Rough QA | 2169 | 1
| ZZ Guzman, Lisandro Rough QA | 11376 | 4
0
0
Kissimmee RNC Total | Total | 15654 | 6 | 3 | 2 | 10%
Melbourne RNC
| ZZ Long, Jordan (ROUGH QA) | 13227 | 7
| ZZ Rogers, Mike (ROUGH QA) | 1989 | 1
0
0
0
Melbourne RNC | Total | 15216 | 8 | 2 | 4 | 20%
N Jacksonville RNC
| ZZ Monk, Adam Rough QA | 20144 | 8
0
0
0
0
N Jacksonville RNC Total | Total | 20144 | 8 | 1 | 8 | 40%
Ocala RNC
| ZZ Boucher, James ROUGH QA | 12696 | 7
0
0
0
0
Ocala RNC Total | Total | 12696 | 7 | 1 | 7 | 35%
Port St Lucie RNC
| ZZ Perlmutter, Mark ROUGH QA | 10001 | 6
0
0
0
0
Port St Lucie RNC Total | Total | 10001 | 6 | 1 | 6 | 30%
S Jacksonville RNC
| ZZ Rose, Geno Rough QA | 28658 | 13
| ZZ Otis, Ditannon Rough QA | 13021 | 7
0
0
0
S Jacksonville RNC Total | Total | 41679 | 20 | 2 | 10 | 50%
Sanford RNC
| ZZ Baker, Chris ROUGH QA | 9396 | 4
| ZZ Bogue, Brandon ROUGH QA | 12343 | 7
| ZZ Continanzi, James ROUGH QA | 0 | 0
| ZZ Meier, Jeremy Rough QA | 4155 | 2
| ZZ Ron Krueger Rough QA | 15484 | 5
0
0
0
0
0
0
0
Sanford RNC Total | Total | 41378 | 18 | 5 | 3.6 | 18%
St Cloud RNC
| ZZ Liles, Isaac Rough QA | 2034 | 1
| ZZ Leon, Humberto Rough QA | 17720 | 9
| ZZ Leija, Diego Rough QA | 7036 | 3
0
0
0
0
St Cloud RNC Total | Total | 26790 | 13 | 3 | 4.3333 | 21.67%
Tampa RNC
| ZZ Concepcion, Gladdys ROUGH QA | 20631 | 1
| ZZ Hooker, Freddie ROUGH QA | 19788 | 0
| ZZ Shannon Chafens Rough QA | 0 | 0
| ZZ Miguel Concepcion ROUGH QA | 31146 | 12
| ZZ Rodriguez, Eder ROUGH QA | 8035 | 4
| ZZ Severe, Anthony ROUGH QA | 2045 | 1
0
0
0
0
Tampa RNC Total | Total | 81645 | 18 | 6 | 3 | 15%
Venice RNC
| ZZ Palmucci, James ROUGH QA | 10367 | 6
| ZZ Rodriguez, Pedro ROUGH QA | 34274 | 17
| ZZ Shannon Chafens Rough QA | 0 | 0
0
0
0
0
0
Venice RNC Total | Total | 44641 | 23 | 3 | 7.6667 | 38.33%
Winter Garden RNC
| ZZ Alderman, Jody Rough QA | 13900 | 5
| ZZ Robles, Jared Rough QA | 8143 | 2
| ZZ Ellis, Berman Rough QA | 10336 | 4
0
0
0
0
0
0
Winter Garden RNC Total | Total | 32379 | 11 | 3 | 3.6667 | 18.33%
Multi-Family
| ZZ Dallos, Francisco Rough QA | 1517 | 1
| ZZ Stratton, Stan Rough QA | 0 | 0
0
0
0
0
0
Multi-Family | Total | 1517 | 1 | 2 | 0.5 | 2.5%
Grand Total | Total | 500460 | 214 | 44 | 4.8636 | 24.32%

## Shop Productivity
|  |  | 1 weeks | 5 | 1230.5825
| Shop | Total Square ft. | crews | avg per crew | avg per day
1 | N Jacksonville RNC | 41123 | 7 | 5874.7143 | 1174.9429 | 95.48%
2 | Brooksville RNC | 91804 | 19 | 4831.7895 | 966.3579 | 78.53%
3 | Winter garden RNC | 53027 | 12 | 4418.9167 | 883.7833 | 71.82%
4 | Ocala RNC | 39335 | 7 | 5619.2857 | 1123.8571 | 91.33%
5 | S Jacksonville RNC | 110264 | 11 | 10024 | 2004.8 | 162.9%
6 | Groveland RNC | 53197 | 10 | 5319.7 | 1063.94 | 86.46%
7 | Venice RNC | 56304 | 11 | 5118.5455 | 1023.7091 | 83.19%
8 | Kissimmee RNC | 75497 | 15 | 5033.1333 | 1006.6267 | 81.8%
9 | Tampa RNC | 107966 | 17 | 6350.9412 | 1270.1882 | 103.2%
10 | St Cloud RNC | 72745 | 16 | 4546.5625 | 909.3125 | 73.89%
11 | Auburndale RNC | 132767 | 22 | 6034.8636 | 1206.9727 | 98.08%
12 | Sanford RNC | 156760 | 26 | 6029.2308 | 1205.8462 | 97.99%
13 | Daytona RNC | 50584 | 11 | 4598.5455 | 919.7091 | 74.74%
14 | Port St Lucie RNC | 22785 | 6 | 3797.5 | 759.5 | 61.72%
15 | Ft Myers RNC | 43842 | 7 | 6263.1429 | 1252.6286 | 101.8%
16 | Melbourne RNC | 39367 | 7 | 5623.8571 | 1124.7714 | 91.4%
17 | Multi-Family | 6372 | 1 | 6372 | 1274.4 | 103.6%